## 01_Company
Engineering Intelligence Platform
HD Systems Design Workbook
Version | 1.0
Last Upadted | 2026-07-22
Property | Value
Company Name | HD Systems
Industry | Engineering Intelligence Software
Business Model | B2B Software as a Service (SaaS)
Headquarters | Charlottesville, Virginia
Founded | 2021
Employees | 250
Engineering & Product Organization | 52
Primary Market | Mid-size and Enterprise Software Development Organizations
Deployment Model | Cloud (AWS)
Development Methodology | Agile / Scrum
Section | Description
Overview | HD Systems develops cloud-based Engineering Intelligence software that helps engineering organizations improve delivery performance, technical capability, operational visibility, and strategic decision-making. The platform collects information from engineering systems such as GitHub, GitLab, Jira, CI/CD pipelines, and cloud platforms, transforming operational data into dashboards, KPIs, and AI-generated executive summaries.
Product | Description
HD Atlas | Engineering portfolio management and roadmap planning
HD Insight | Executive dashboards, KPIs, and engineering analytics
HD Connect | Integration platform for engineering tools
HD Secure | Security, compliance, and vulnerability intelligence
HD Cloud | Cloud infrastructure monitoring and optimization
HD Admin | Administration, configuration, and user management
Technology Stack | Purpose
Python | Synthetic data generation and enrichment
PostgreSQL | Operational database
Grafana | Dashboards and analytics
Docker | Local development environment
GitHub | Source control
OpenAI | AI-generated executive summaries
VS Code | Development environment
Topic | Description
Project Goal | Demonstrate an end-to-end Engineering Intelligence platform using realistic synthetic data.
Data Pipeline | Workbook → Python Loader → PostgreSQL → Grafana → AI Executive Summary
Intended Audience | Hiring managers, engineering leaders, product managers, and technical interviewers.
Disclaimer | All data contained within this workbook is fictional and intended solely for demonstration, educational, and portfolio purposes.

## 02_Departments
department_name | description
Platform Engineering | Builds and maintains the shared platform services that support all HD Systems products.
Analytics Engineering | Develops dashboards, metrics, reporting, and engineering intelligence capabilities.
Integration Engineering | Builds and maintains integrations with GitHub, GitLab, Jira, and other engineering systems.
Cloud Platform | Manages AWS infrastructure, deployments, observability, and site reliability.
Security Engineering | Oversees application security, compliance, vulnerability management, and secure development practices.
Quality Engineering | Owns testing strategy, test automation, quality metrics, and release validation.
Product Management | Defines product vision, roadmaps, feature prioritization, and customer requirements.
Administration Services | Supports user administration, licensing, internal tools, and operational processes.
Executive Leadership | Provides strategic leadership and executive oversight for the company.

## 03_Teams
team_name | department_name | team_lead_title | mission
Platform Core | Platform Engineering | Director of Platform Engineering | Develops and maintains the core platform services shared across all HD Systems products.
Developer Experience | Platform Engineering | Engineering Manager | Improves developer productivity through internal tools, automation, and platform improvements.
Analytics Platform | Analytics Engineering | Engineering Manager | Builds dashboards, KPIs, reporting services, and engineering intelligence capabilities.
AI & Insights | Analytics Engineering | Senior Engineering Manager | Develops AI-powered insights, executive summaries, and predictive analytics.
Integration Services | Integration Engineering | Engineering Manager | Builds integrations with GitHub, GitLab, Jira, Azure DevOps, and third-party platforms.
API Platform | Integration Engineering | Technical Lead | Develops and maintains public APIs and internal service integrations.
Cloud Operations | Cloud Platform | Director of Cloud Operations | Manages AWS infrastructure, deployments, observability, and operational reliability.
DevSecOps | Cloud Platform | Engineering Manager | Automates deployments while integrating security throughout the delivery pipeline.
Application Security | Security Engineering | Security Engineering Manager | Performs secure code reviews, vulnerability management, and compliance activities.
Quality Automation | Quality Engineering | QA Manager | Develops automated testing frameworks and release validation processes.
Product Strategy | Product Management | Director of Product Management | Defines product vision, roadmaps, customer priorities, and release planning.
Customer Success Engineering | Administration Services | Operations Manager | Supports customer onboarding, licensing, user administration, and operational support.
Executive Leadership | Executive Leadership | Chief Executive Officer | Executive leadership and company strategy

## 04_Employees
employee_number | first_name | last_name | email | title | role_type | department | team | manager | location | hire_date | status
EMP000 | Alex | Morgan | alex.morgan@hdsystems.com | Chief Executive Officer | Executive | Executive Leadership | Executive Leadership |  | Charlottesville, VA | 2021-01-04 | Active
EMP001 | Sarah | Mitchell | sarah.mitchell@hdsystems.com | VP of Engineering | Leadership | Platform Engineering | Platform Core |  | Charlottesville, VA | 2021-03-15 | Active
EMP002 | Michael | Chen | michael.chen@hdsystems.com | Director of Platform Engineering | Leadership | Platform Engineering | Platform Core | EMP001 | Charlottesville, VA | 2021-05-10 | Active
EMP003 | Emily | Rodriguez | emily.rodriguez@hdsystems.com | Director of Product Management | Leadership | Product Management | Product Strategy |  | Charlottesville, VA | 2021-04-05 | Active
EMP004 | David | Kim | david.kim@hdsystems.com | Director of Cloud Operations | Leadership | Cloud Platform | Cloud Operations | EMP001 | Charlottesville, VA | 2022-01-17 | Active
EMP005 | Jennifer | Patel | jennifer.patel@hdsystems.com | Security Engineering Manager | Leadership | Security Engineering | Application Security | EMP001 | Remote | 2022-03-01 | Active
EMP006 | Brian | Thompson | brian.thompson@hdsystems.com | Senior Engineering Manager | Leadership | Analytics Engineering | AI & Insights | EMP001 | Remote | 2022-02-14 | Active
EMP007 | Lisa | Walker | lisa.walker@hdsystems.com | Engineering Manager | Leadership | Analytics Engineering | Analytics Platform | EMP006 | Remote | 2022-07-11 | Active
EMP008 | Kevin | Foster | kevin.foster@hdsystems.com | Engineering Manager | Leadership | Integration Engineering | Integration Services | EMP001 | Remote | 2022-08-22 | Active
EMP009 | Amanda | Brooks | amanda.brooks@hdsystems.com | QA Manager | Leadership | Quality Engineering | Quality Automation | EMP001 | Charlottesville, VA | 2022-05-02 | Active
EMP010 | Ryan | Edwards | ryan.edwards@hdsystems.com | Operations Manager | Leadership | Administration Services | Customer Success Engineering | EMP003 | Charlottesville, VA | 2022-06-13 | Active

## 05_Products
product_name | owning_team | product_manager_title | primary_purpose | target_users | maturity
HD Atlas | Product Strategy | Senior Product Manager | Engineering portfolio management, roadmaps, and strategic planning. | Engineering Leadership | Mature
HD Insight | Analytics Platform | Product Manager | Executive dashboards, KPIs, engineering metrics, and AI-powered reporting. | Engineering Managers & Executives | Mature
HD Connect | Integration Services | Product Manager | Integrates engineering tools including GitHub, GitLab, Jira, Azure DevOps, and CI/CD systems. | Development Teams | Growing
HD Secure | Application Security | Senior Product Manager | Security posture, vulnerability tracking, compliance, and secure development analytics. | Security & Compliance Teams | Growing
HD Cloud | Cloud Operations | Product Manager | Cloud infrastructure monitoring, cost optimization, deployments, and operational health. | Cloud Operations Teams | Mature
HD Admin | Customer Success Engineering | Product Owner | User management, licensing, system administration, and platform configuration. | System Administrators | Mature

## 06_Projects
project_name | customer_name | product_name | owning_team | project_manager | status | priority | start_date | target_date
Executive Engineering Dashboard | Acme Financial | HD Insight | Analytics Platform | EMP004 | Active | High | 2025-01-15 | 2025-08-30
Enterprise Identity Integration | BlueSky Health | HD Connect | Integration Services | EMP005 | Active | Critical | 2025-02-01 | 2025-10-31
Cloud Infrastructure Modernization | Nova Manufacturing | HD Cloud | Cloud Operations | EMP006 | Active | High | 2025-03-10 | 2025-12-15
Secure Application Compliance | Pinnacle Energy | HD Secure | Application Security | EMP007 | Active | Critical | 2025-01-20 | 2025-11-30
Executive Portfolio Analytics | Horizon Retail Group | HD Insight | Analytics Platform | EMP004 | Planning | Medium | 2025-05-01 | 2025-12-31
Customer Administration Portal | City of Charlottesville | HD Admin | Customer Success Engineering | EMP008 | Active | Medium | 2025-04-15 | 2025-09-30
Cloud Cost Optimization | Summit Telecom | HD Cloud | Cloud Operations | EMP006 | Planning | High | 2025-06-01 | 2026-01-31
Cross-Platform Data Integration | BrightPath Logistics | HD Connect | Integration Services | EMP005 | Active | High | 2025-02-20 | 2025-10-15

## 07_Customers
customer_name | industry | company_size | region | customer_tier | active | onboarding_date
Acme Financial | Financial Services | Enterprise | North America | Strategic | TRUE | 2022-01-15
BlueSky Health | Healthcare | Enterprise | North America | Strategic | TRUE | 2021-09-08
Horizon Retail Group | Retail | Mid-Market | Europe | Gold | TRUE | 2023-03-22
Nova Manufacturing | Manufacturing | Enterprise | Asia-Pacific | Gold | TRUE | 2022-11-10
City of Charlottesville | Government | SMB | North America | Standard | TRUE | 2024-02-01
Pinnacle Energy | Energy | Enterprise | North America | Strategic | TRUE | 2021-05-17
Summit Telecom | Telecommunications | Enterprise | Europe | Gold | TRUE | 2023-06-12
BrightPath Logistics | Transportation & Logistics | Mid-Market | North America | Silver | TRUE | 2024-01-09
GreenLeaf Agriculture | Agriculture | Mid-Market | North America | Standard | TRUE | 2024-04-18
Apex Insurance Group | Insurance | Enterprise | Europe | Gold | TRUE | 2022-08-30

## 08_Technologies
Technology | Category
PostgreSQL | Database
Grafana | Observability
Kubernetes | Cloud
Terraform | Cloud
Java | Backend
Python | Backend
React | Frontend
Docker | Cloud
GitLab CI | DevOps

## 09_Issue_Templates
Type | Example
Feature | Add SCIM provisioning support
Bug | Fix dashboard filtering issue
Technical Debt | Refactor Terraform modules
Performance | Optimize PostgreSQL queries

## 10_Labels
Label | Category
priority::high | Priority
bug | Type
enhancement | Type
security | Theme
performance | Theme

## 11_Skills
Skill | Category | Keywords | Active
Kubernetes | Container Platform | kubernetes,k8s,kube,kubectl,pod,deployment,service,ingress,namespace,cluster,container orchestration,container | Y
AWS EKS | Cloud Platform | aws eks,elastic kubernetes service,aws kubernetes,managed k8s,fargate | Y
RKE | Container Platform | rke,rancher kubernetes engine,rke1,rke2,k3s,rancher | Y
Istio | Service Mesh | istio,service mesh,envoy,sidecar,virtualservice,destinationrule,gateway,mtls,kiali,jaeger | Y
AWS EC2 | Cloud Platform | ec2,ec2 instance,instance,amazon ec2 | Y
AWS S3 | Cloud Storage | s3,s3 bucket,bucket,object storage,amazon s3 | Y
AWS VPC | Cloud Networking | vpc,subnet,security group,vpc subnet,amazon vpc | Y
AWS IAM | Identity & Access | iam,iam role,role,policy,identity and access management | Y
AWS ALB | Cloud Networking | alb,application load balancer,load balancer,alb listener | Y
AWS RDS | Database | rds,rds instance,aurora,amazon rds | Y
Prometheus | Observability | prometheus,monitoring,metrics,promql,alertmanager,time series,scraping | Y
Grafana | Observability | grafana,dashboard,visualization,metrics,monitoring,prometheus query | Y
Tempo | Observability | tempo,distributed tracing,traces,zipkin | Y
Loki | Observability | loki,log aggregation,logging,promtail,logql | Y
Keycloak | Identity & Access | keycloak,identity management,access management,sso,openid connect,oauth2,saml,authentication,authorization,realm,user federation | Y
SAML | Identity & Access | saml,saml assertion,service provider,identity provider,sp,idp | Y
OAuth 2.0 | Identity & Access | oauth,oauth2,access token,refresh token,bearer token | Y
OpenID Connect (OIDC) | Identity & Access | oidc,openid connect,id token | Y
SSO Troubleshooting | Identity & Access | single sign-on,login failed,authentication error,authorization issue,redirect loop,saml response,oauth token,oidc flow,debug sso,troubleshoot login | Y
Terraform | Infrastructure as Code | terraform,iac,infrastructure as code,tf,terraform plan,terraform apply,state file,tfstate,hcl,module,provider | Y
Terragrunt | Infrastructure as Code | terragrunt,terraform wrapper,dry,remote state management,locking | Y
Crossplane | Infrastructure as Code | crossplane,kubernetes crd,control plane,composition,managed resource | Y
GitLab CI/CD | DevOps | gitlab ci/cd,gitlab pipeline,ci cd,.gitlab-ci.yml,runner,job,stage,artifact,continuous integration,continuous deployment,deployment pipeline,build pipeline | Y
ArgoCD | GitOps | argocd,argo,gitops,application sync,reconciliation,appproject | Y
Flux | GitOps | flux,fluxcd,gitops,kustomization,helmrelease,reconciliation | Y
Zarf | DevOps | zarf,air gap deployment,airgap,disconnected environment,zarf package,big bang | Y
Helm | Kubernetes | helm,helm chart,helm release,values.yaml,helm install,helm upgrade,template | Y
Bash | Programming Language | bash,shell script,bash script,sh,scripting,terminal,command line | Y
Python | Programming Language | python,python script,py,pip,virtualenv,django,flask | Y
JavaScript | Programming Language | javascript,js,node.js,npm,yarn,react,angular,vue | Y
Golang | Programming Language | golang,go,goroutine,microservice,concurrency,go build,go run,panic,fmt,func | Y
Java | Programming Language | java,jvm,jdk,spring,spring boot,maven,gradle,jar,war | Y
YAML | Configuration | yaml,yaml file,configuration file,manifest,k8s manifest,ansible playbook | Y
NeuVector | Security | neuvector,container security,runtime security,vulnerability scanning,network segmentation,admission control | Y
Kyverno | Kubernetes Security | kyverno,kubernetes policy engine,policy management,admission control,validate policy,mutate policy,generate policy,background scan | Y
SonarQube | Code Quality | sonarqube,static code analysis,code quality,security scanning,vulnerabilities,bugs,code smells,sq | Y
Microsoft Teams | Collaboration | ms teams,microsoft teams,teams,chat,channel,meeting,collaboration | Y
Mattermost | Collaboration | mattermost,chat,channel,collaboration,self-hosted chat | Y
Runbook Authoring | Documentation | runbook,playbook,standard operating procedure,sop,incident response,troubleshooting guide,documentation,docs | Y
External Secrets Operator | Secrets Management | external secrets operator,eso,kubernetes secrets,vault integration,aws secrets manager,gcp secret manager,secret management | Y
ADI Creation | Platform Administration | adi creation,application deployment instance,adi,new environment,onboarding application,tenant setup | Y
Okta | Identity & Access | okta,identity management,sso,mfa,multi-factor authentication,universal directory,api access management,okta integration | Y
Public Key Infrastructure (PKI) | Security | public key infrastructure,pki,certificate,cert,tls,ssl,certificate authority,public key,private key,encryption,digital signature,cert rotation,openssl | Y
PostgreSQL | Database | postgresql,postgres,pgsql,pgadmin,psql,relational database | Y
Redis | Database | redis,in-memory database,key-value store,cache | Y
Valkey | Database | valkey,key-value store,in-memory database | Y
Amazon ElastiCache | Cloud Platform | elasticache,amazon elasticache,managed redis | Y
RabbitMQ | Messaging | rabbitmq,message queue,mq,message broker,amqp,producer,consumer,exchange,queue | Y
MySQL | Database | mysql,mysql database,mariadb,relational database | Y
Docker | Container Platform | docker,container,image,dockerfile,docker compose | Y
Git | Version Control | git,repository,commit,branch,pull request,merge | Y
Y

## 12_Themes
Theme | Description | Keywords | Active
Technical Debt | Reduce maintenance burden and improve code quality | refactor,legacy,workaround,manual process,outdated,deprecated,technical debt,brittle,cleanup,cleanup task,rewrite,modernize | Y
Security | Protect the platform and reduce risk | security,vulnerability,cve,iam,rbac,policy,threat,scan,sast,dast,hardening,compliance,certificate,pki,encryption,mfa | Y
Migration | Move systems, users, or services to a new platform | migration,migrate,upgrade,cutover,transition,okta,move,replace,consolidate | Y
Access: Tool & Service | Provision or manage access to engineering tools and services | access,permission,argo,argocd,gitlab,nexus,neuvector,grafana,kibana,harbor,onboarding,onboard,account,service access | Y
Access: Authentication & Tokens | Authentication, identity providers, and credential management | login,keycloak,sso,auth,authentication,token,credentials,unauthorized,401,403,cac,smart card,okta,adfs,oidc,oauth,saml | Y
Access: Permissions & Roles | Authorization and role management | role,roles,permission,permissions,privilege,privileges,maintainer,developer,admin,trusted deployer,readonly,rbac,least privilege | Y
Platform: Network & Connectivity | Networking and communication between services | network,connect,connectivity,firewall,nlb,alb,vpc,dns,route,routing,cors,endpoint,timeout,unreachable,503,502,load balancer | Y
Platform: Backing Services | Databases, storage, messaging, and shared platform services | db,database,rds,postgres,postgresql,mysql,redis,s3,pvc,vault,eso,secrets,rabbitmq,smtp,storage,persistent volume | Y
Platform: Cluster & Namespace Management | Kubernetes infrastructure and environment management | environment,platform,cluster,namespace,il4,il6,staging,prod,production,dev,node,autoscaling,kyverno,istio,kubernetes,k8s | Y
Platform: Deployment & CI/CD | Application deployment and release automation | deploy,deployment,pipeline,image,container,helm,chart,argo application,sync,rollout,rollback,ci/cd,continuous integration,continuous deployment,gitops,terraform,iac | Y
Database Management | Database administration and optimization | sql,migration,backup,restore,purge,schema,query,index,indexes,flyway,ddl,dml,postgres,mysql | Y
Integrations & Connectivity | APIs and system-to-system integrations | integration,integrations,s2s,peer,api,rest,graphql,webhook,connector,synchronize,sync | Y
Feature & Enhancement Requests | New functionality or user-requested improvements | request,feature,enhancement,add,create,support,capability,improve,allow,enable,provide,need,want,would like,new functionality | Y
Observability | Monitoring, logging, alerting, and operational visibility | grafana,prometheus,loki,tempo,dashboard,monitoring,metrics,logging,tracing,alert,alertmanager,observability | Y
Performance | Improve speed, scalability, or efficiency | performance,optimize,optimization,latency,throughput,slow,response time,caching,scale,scalability,faster,efficient | Y
Reliability & Availability | Improve stability and reduce outages | reliability,availability,failover,resiliency,resilience,redundancy,high availability,ha,recovery,incident,outage,restart,self-healing | Y
Automation | Eliminate manual work through automation | automate,automation,automated,script,scripting,scheduled,cron,workflow,orchestration | Y
Documentation | Improve operational knowledge and documentation | documentation,document,runbook,playbook,sop,guide,knowledge base,wiki,instructions | Y
AI & Analytics | Artificial intelligence, reporting, and data insights | ai,openai,llm,gpt,analytics,reporting,dashboard,executive summary,insights,prediction | Y

## 13_Issues
issue_key | project_name | title | description | labels | issue_type | priority | severity | status | assignee | weight | created_date | closed_date
HDI-101 | Executive Engineering Dashboard | Implement Executive KPI Dashboard | Create Grafana executive dashboard using PostgreSQL metrics. | grafana,dashboard,postgres,metrics | Feature | High | Medium | In Progress | EMP004 | 8 | 2026-06-01
HDI-102 | Executive Engineering Dashboard | Optimize Dashboard SQL Queries | Refactor PostgreSQL queries and indexes. | postgres,performance,sql | Technical Debt | High | Low | Open | EMP005 | 5 | 2026-06-02
HDI-103 | Executive Engineering Dashboard | Executive PDF Export | Export dashboards to PDF. | grafana,reporting,pdf | Feature | Medium | Low | Open | EMP006 | 3 | 2026-06-03
HDI-104 | Executive Engineering Dashboard | Sprint Velocity Widget | Display sprint metrics. | grafana,metrics,sprint | Feature | Medium | Low | Review | EMP004 | 5 | 2026-06-04
HDI-105 | Executive Engineering Dashboard | Role-Based Dashboard Access | Secure dashboards with Keycloak OAuth2. | security,keycloak,oauth | Security | High | High | Open | EMP003 | 8 | 2026-06-05
EII-101 | Enterprise Identity Integration | Configure Keycloak OIDC | Implement OpenID Connect authentication. | keycloak,oidc,oauth,security | Security | High | High | In Progress | EMP003 | 8 | 2026-06-01
EII-102 | Enterprise Identity Integration | Implement SAML SSO | Add SAML authentication. | saml,sso,keycloak | Feature | High | Medium | Open | EMP003 | 5 | 2026-06-03
EII-103 | Enterprise Identity Integration | Rotate PKI Certificates | Automate certificate renewal. | pki,certificate,security | Security | High | High | Open | EMP003 | 5 | 2026-06-06
EII-104 | Enterprise Identity Integration | Implement RBAC Policies | Create Kubernetes RBAC roles. | kubernetes,rbac,security | Security | Medium | Medium | Review | EMP009 | 5 | 2026-06-08
CIM-101 | Cloud Infrastructure Modernization | Deploy Grafana with Helm | Deploy Grafana using Helm and ArgoCD. | grafana,kubernetes,helm,argocd | Feature | High | Medium | Review | EMP009 | 8 | 2026-06-01
CIM-102 | Cloud Infrastructure Modernization | Configure Prometheus Metrics | Collect Prometheus metrics. | prometheus,metrics,kubernetes | Feature | Medium | Low | Open | EMP009 | 5 | 2026-06-02
CIM-103 | Cloud Infrastructure Modernization | Enable Loki Log Aggregation | Centralize logs. | loki,logging,grafana | Feature | Medium | Low | Open | EMP010 | 3 | 2026-06-03
CIM-104 | Cloud Infrastructure Modernization | Terraform VPC Deployment | Deploy AWS networking. | terraform,aws,vpc,iac | Feature | High | Medium | In Progress | EMP009 | 8 | 2026-06-04
SAC-101 | Secure Application Compliance | Scan Images with NeuVector | Integrate vulnerability scanning. | neuvector,security,kubernetes | Security | High | High | Open | EMP010 | 5 | 2026-06-05
SAC-102 | Secure Application Compliance | SonarQube Quality Gates | Enforce quality gates. | sonarqube,quality,security | Feature | Medium | Low | Open | EMP005 | 3 | 2026-06-06
SAC-103 | Secure Application Compliance | Secrets Management | Integrate External Secrets Operator. | eso,kubernetes,security | Feature | Medium | Medium | Open | EMP010 | 5 | 2026-06-07
SAC-104 | Secure Application Compliance | Compliance Reporting | Generate compliance dashboard. | security,grafana,reporting | Feature | Medium | Low | Review | EMP004 | 5 | 2026-06-08
EPA-101 | Executive Portfolio Analytics | Load Engineering Metrics | Populate analytics tables. | python,etl,postgres | Feature | High | Low | Done | EMP005 | 5 | 2026-06-01 | 2026-06-05
EPA-102 | Executive Portfolio Analytics | Generate AI Executive Summary | Summarize engineering progress. | openai,ai,python | Feature | High | Low | In Progress | EMP004 | 8 | 2026-06-03
EPA-103 | Executive Portfolio Analytics | Extract Skills from Issues | Scan title description and labels. | python,skills,nlp,keywords | Feature | High | Low | Open | EMP005 | 8 | 2026-06-04
EPA-104 | Executive Portfolio Analytics | Portfolio Health Score | Calculate engineering health. | analytics,kpi,grafana | Feature | Medium | Low | Open | EMP004 | 5 | 2026-06-05
CAP-101 | Customer Administration Portal | Build Customer Search | Implement customer directory. | python,postgres,ui | Feature | Medium | Low | Done | EMP006 | 3 | 2026-06-01 | 2026-06-04
CAP-102 | Customer Administration Portal | Customer Audit Trail | Track administrative changes. | audit,postgres,security | Feature | Medium | Low | Open | EMP006 | 5 | 2026-06-02
CAP-103 | Customer Administration Portal | Account Provisioning | Automate ADI onboarding. | adi,onboarding,automation | Enhancement | Medium | Low | Open | EMP003 | 3 | 2026-06-03
CCO-101 | Cloud Cost Optimization | AWS Cost Dashboard | Visualize cloud spend. | aws,grafana,cost | Feature | High | Low | In Progress | EMP009 | 5 | 2026-06-02
CCO-102 | Cloud Cost Optimization | Idle Resource Detection | Identify underutilized EC2. | aws,ec2,cost | Enhancement | Medium | Low | Open | EMP009 | 3 | 2026-06-03
CCO-103 | Cloud Cost Optimization | Reserved Instance Analysis | Recommend RI purchases. | aws,analytics,cost | Feature | Medium | Low | Open | EMP005 | 5 | 2026-06-04
CPDI-101 | Cross-Platform Data Integration | Build GitHub REST Connector | Synchronize GitHub issues into PostgreSQL. | github,rest,python,postgres | Feature | High | Medium | In Progress | EMP007 | 8 | 2026-06-01
CPDI-102 | Cross-Platform Data Integration | Import GitLab Issues | Synchronize GitLab issues. | gitlab,python,api | Feature | High | Medium | Done | EMP008 | 5 | 2026-06-02 | 2026-06-08
CPDI-103 | Cross-Platform Data Integration | Normalize Issue Schema | Map GitHub and GitLab fields. | database,postgres,etl | Technical Debt | Medium | Low | Open | EMP005 | 5 | 2026-06-03
CPDI-104 | Cross-Platform Data Integration | Azure DevOps Prototype | Prototype Azure DevOps ingestion. | azure,rest,python | Spike | Low | Low | Open | EMP007 | 5 | 2026-06-04
HDI-106 | Executive Engineering Dashboard | Add drill-down to skills coverage dashboard | Executives want to click from the skills coverage dashboard into the underlying issue detail. Add Grafana data links and a detail table panel backed by a PostgreSQL view. | grafana,dashboard,postgres,drill-down | Feature | Critical | Critical | Open | EMP003 | 5 | 2026-07-18
HDI-107 | Executive Engineering Dashboard | Optimize slow PostgreSQL query behind issue aging panel | The issue aging panel takes over 8 seconds to render. Query plan shows a sequential scan; add indexes and rewrite the aggregation to improve response time and reduce latency. | postgres,performance,query,index | Performance | High | High | Review | EMP005 | 5 | 2026-07-28
HDI-108 | Executive Engineering Dashboard | Dashboard variables reset after time range change | Selecting a new time range clears the customer and project filter variables. Users lose their filter state and must reselect. Investigate Grafana variable persistence. | grafana,bug,filters,dashboard | Bug | Medium | Medium | Done | EMP004 | 8 | 2026-06-26 | 2026-07-12
HDI-109 | Executive Engineering Dashboard | Add Prometheus metrics for ETL pipeline | Instrument the workbook import and GitHub sync with Prometheus metrics so we can monitor load duration, record counts, and failures in Grafana with alerting. | prometheus,metrics,monitoring,etl | Feature | Medium | Medium | Review | EMP004 | 13 | 2026-07-16
HDI-110 | Executive Engineering Dashboard | Scheduled PDF export of executive dashboard | Leadership wants a weekly PDF export of the executive dashboard emailed automatically. Evaluate Grafana reporting options and schedule generation via cron automation. | grafana,pdf,report,automation | Feature | Critical | High | Open | EMP005 | 5 | 2026-03-28
HDI-111 | Executive Engineering Dashboard | Cache expensive aggregation queries with Redis | Repeated dashboard loads re-run heavy aggregations. Introduce a Redis cache for pre-computed rollups to improve dashboard response time. | redis,cache,performance,postgres | Performance | Medium | Medium | Open | EMP006 | 8 | 2026-05-11
HDI-112 | Executive Engineering Dashboard | Row-level security for customer-scoped dashboards | Customer success engineers should only see dashboards for their assigned customers. Implement role-based access with RBAC policies and PostgreSQL row filters. | rbac,security,postgres,grafana | Feature | High | High | In Progress | EMP005 | 8 | 2025-08-02
HDI-113 | Executive Engineering Dashboard | Refactor legacy KPI SQL views | The original KPI views contain duplicated logic and outdated column names. Refactor into layered views with consistent naming to reduce technical debt. | postgres,refactor,technical-debt,views | Technical Debt | Medium | Medium | Done | EMP005 | 8 | 2026-04-04 | 2026-04-07
HDI-114 | Executive Engineering Dashboard | Sprint velocity trend widget | Add a panel showing weekly completed weight per team so managers can track velocity trends and spot delivery slowdowns early. | grafana,velocity,metrics,dashboard | Feature | Medium | Medium | Done | EMP006 | 13 | 2026-05-10 | 2026-05-17
HDI-115 | Executive Engineering Dashboard | Fix timezone drift in created_date reporting | Issues created late in the evening appear under the wrong day in dashboards. Normalize timestamps to UTC in the ETL and cast to date at query time. | bug,timezone,etl,postgres | Bug | Low | Low | Done | EMP007 | 2 | 2026-02-21 | 2026-02-26
HDI-116 | Executive Engineering Dashboard | AI executive summary panel formatting | The AI-generated executive summary renders raw markdown in the panel. Improve the rendering, and add loading and error states for the AI analytics endpoint. | ai,llm,dashboard,markdown | Bug | High | Critical | Open | EMP004 | 5 | 2026-05-22
HDI-117 | Executive Engineering Dashboard | Alerting on stale data imports | If the nightly import fails silently the dashboards show stale data. Add freshness metrics and Grafana alerting when the last successful load is older than 24 hours. | alerting,monitoring,etl,grafana | Feature | Medium | Low | Done | EMP004 | 3 | 2026-07-11 | 2026-07-15
HDI-118 | Executive Engineering Dashboard | Add drill-down to skills coverage dashboard - phase 2 | Executives want to click from the skills coverage dashboard into the underlying issue detail. Add Grafana data links and a detail table panel backed by a PostgreSQL view. | grafana,dashboard,postgres,drill-down | Feature | Medium | Medium | In Progress | EMP007 | 5 | 2025-08-04
HDI-119 | Executive Engineering Dashboard | Optimize slow PostgreSQL query behind portfolio health panel (staging) | The portfolio health panel takes over 8 seconds to render. Query plan shows a sequential scan; add indexes and rewrite the aggregation to improve response time and reduce latency. | postgres,performance,query,index | Performance | Medium | Medium | Open | EMP007 | 3 | 2026-05-20
HDI-120 | Executive Engineering Dashboard | Dashboard variables reset after time range change follow-up | Selecting a new time range clears the customer and project filter variables. Users lose their filter state and must reselect. Investigate Grafana variable persistence. | grafana,bug,filters,dashboard | Bug | Medium | High | Review | EMP005 | 5 | 2026-05-25
HDI-121 | Executive Engineering Dashboard | Add Prometheus metrics for ETL pipeline (production) | Instrument the workbook import and GitHub sync with Prometheus metrics so we can monitor load duration, record counts, and failures in Grafana with alerting. | prometheus,metrics,monitoring,etl | Feature | Low | Medium | Done | EMP003 | 13 | 2026-05-26 | 2026-05-30
HDI-122 | Executive Engineering Dashboard | Scheduled PDF export of executive dashboard follow-up | Leadership wants a weekly PDF export of the executive dashboard emailed automatically. Evaluate Grafana reporting options and schedule generation via cron automation. | grafana,pdf,report,automation | Feature | High | High | Open | EMP003 | 5 | 2026-07-27
HDI-123 | Executive Engineering Dashboard | Cache expensive aggregation queries with Redis - phase 2 | Repeated dashboard loads re-run heavy aggregations. Introduce a Redis cache for pre-computed rollups to improve dashboard response time. | redis,cache,performance,postgres | Performance | Medium | Medium | Open | EMP004 | 8 | 2026-06-01
HDI-124 | Executive Engineering Dashboard | Row-level security for customer-scoped dashboards for EU region | Customer success engineers should only see dashboards for their assigned customers. Implement role-based access with RBAC policies and PostgreSQL row filters. | rbac,security,postgres,grafana | Feature | High | Critical | Open | EMP004 | 13 | 2026-05-09
HDI-125 | Executive Engineering Dashboard | Refactor legacy KPI SQL views - phase 2 | The original KPI views contain duplicated logic and outdated column names. Refactor into layered views with consistent naming to reduce technical debt. | postgres,refactor,technical-debt,views | Technical Debt | Medium | Medium | Done | EMP004 | 5 | 2026-06-04 | 2026-06-11
HDI-126 | Executive Engineering Dashboard | Sprint velocity trend widget follow-up | Add a panel showing weekly completed weight per team so managers can track velocity trends and spot delivery slowdowns early. | grafana,velocity,metrics,dashboard | Feature | Critical | High | Done | EMP004 | 3 | 2026-01-01 | 2026-01-09
HDI-127 | Executive Engineering Dashboard | Fix timezone drift in created_date reporting for EU region | Issues created late in the evening appear under the wrong day in dashboards. Normalize timestamps to UTC in the ETL and cast to date at query time. | bug,timezone,etl,postgres | Bug | High | Medium | Review | EMP005 | 3 | 2026-05-03
HDI-128 | Executive Engineering Dashboard | AI executive summary panel formatting - phase 2 | The AI-generated executive summary renders raw markdown in the panel. Improve the rendering, and add loading and error states for the AI analytics endpoint. | ai,llm,dashboard,markdown | Bug | High | High | Open | EMP004 | 8 | 2026-07-25
HDI-129 | Executive Engineering Dashboard | Alerting on stale data imports (staging) | If the nightly import fails silently the dashboards show stale data. Add freshness metrics and Grafana alerting when the last successful load is older than 24 hours. | alerting,monitoring,etl,grafana | Feature | Medium | Medium | Done | EMP003 | 13 | 2025-10-08 | 2025-10-24
HDI-130 | Executive Engineering Dashboard | Add drill-down to portfolio health dashboard for EU region | Executives want to click from the portfolio health dashboard into the underlying issue detail. Add Grafana data links and a detail table panel backed by a PostgreSQL view. | grafana,dashboard,postgres,drill-down | Feature | Medium | Low | Done | EMP006 | 5 | 2025-11-23 | 2025-11-28
HDI-131 | Executive Engineering Dashboard | Optimize slow PostgreSQL query behind portfolio health panel (staging) | The portfolio health panel takes over 8 seconds to render. Query plan shows a sequential scan; add indexes and rewrite the aggregation to improve response time and reduce latency. | postgres,performance,query,index | Performance | Medium | Medium | Open | EMP005 | 5 | 2026-07-15
HDI-132 | Executive Engineering Dashboard | Dashboard variables reset after time range change - phase 2 | Selecting a new time range clears the customer and project filter variables. Users lose their filter state and must reselect. Investigate Grafana variable persistence. | grafana,bug,filters,dashboard | Bug | Critical | High | Done | EMP005 | 3 | 2025-08-05 | 2025-08-20
HDI-133 | Executive Engineering Dashboard | Add Prometheus metrics for ETL pipeline (staging) | Instrument the workbook import and GitHub sync with Prometheus metrics so we can monitor load duration, record counts, and failures in Grafana with alerting. | prometheus,metrics,monitoring,etl | Feature | Medium | Low | Done | EMP004 | 5 | 2025-11-08 | 2025-11-19
HDI-134 | Executive Engineering Dashboard | Scheduled PDF export of executive dashboard for EU region | Leadership wants a weekly PDF export of the executive dashboard emailed automatically. Evaluate Grafana reporting options and schedule generation via cron automation. | grafana,pdf,report,automation | Feature | Medium | Medium | Done | EMP004 | 5 | 2025-12-19 | 2025-12-27
HDI-135 | Executive Engineering Dashboard | Cache expensive aggregation queries with Redis (production) | Repeated dashboard loads re-run heavy aggregations. Introduce a Redis cache for pre-computed rollups to improve dashboard response time. | redis,cache,performance,postgres | Performance | Medium | Medium | Done | EMP004 | 8 | 2026-06-22 | 2026-06-27
HDI-136 | Executive Engineering Dashboard | Row-level security for customer-scoped dashboards follow-up | Customer success engineers should only see dashboards for their assigned customers. Implement role-based access with RBAC policies and PostgreSQL row filters. | rbac,security,postgres,grafana | Feature | Low | Medium | Open | EMP007 | 13 | 2026-07-01
HDI-137 | Executive Engineering Dashboard | Refactor legacy KPI SQL views (production) | The original KPI views contain duplicated logic and outdated column names. Refactor into layered views with consistent naming to reduce technical debt. | postgres,refactor,technical-debt,views | Technical Debt | Medium | High | Done | EMP006 | 5 | 2026-05-03 | 2026-05-05
HDI-138 | Executive Engineering Dashboard | Sprint velocity trend widget (production) | Add a panel showing weekly completed weight per team so managers can track velocity trends and spot delivery slowdowns early. | grafana,velocity,metrics,dashboard | Feature | High | Critical | In Progress | EMP006 | 5 | 2026-07-23
HDI-139 | Executive Engineering Dashboard | Fix timezone drift in created_date reporting follow-up | Issues created late in the evening appear under the wrong day in dashboards. Normalize timestamps to UTC in the ETL and cast to date at query time. | bug,timezone,etl,postgres | Bug | Critical | Critical | Done | EMP007 | 1 | 2026-06-28 | 2026-07-13
HDI-140 | Executive Engineering Dashboard | AI executive summary panel formatting - phase 2 | The AI-generated executive summary renders raw markdown in the panel. Improve the rendering, and add loading and error states for the AI analytics endpoint. | ai,llm,dashboard,markdown | Bug | Critical | Critical | Done | EMP005 | 3 | 2026-01-25 | 2026-02-19
HDI-141 | Executive Engineering Dashboard | Alerting on stale data imports for EU region | If the nightly import fails silently the dashboards show stale data. Add freshness metrics and Grafana alerting when the last successful load is older than 24 hours. | alerting,monitoring,etl,grafana | Feature | Critical | Critical | In Progress | EMP003 | 8 | 2026-07-16
HDI-142 | Executive Engineering Dashboard | Add drill-down to customer tier dashboard for EU region | Executives want to click from the customer tier dashboard into the underlying issue detail. Add Grafana data links and a detail table panel backed by a PostgreSQL view. | grafana,dashboard,postgres,drill-down | Feature | Critical | Critical | Review | EMP005 | 8 | 2026-06-08
HDI-143 | Executive Engineering Dashboard | Optimize slow PostgreSQL query behind risk overview panel follow-up | The risk overview panel takes over 8 seconds to render. Query plan shows a sequential scan; add indexes and rewrite the aggregation to improve response time and reduce latency. | postgres,performance,query,index | Performance | Critical | Critical | In Progress | EMP007 | 5 | 2026-06-06
EII-105 | Enterprise Identity Integration | Keycloak realm export breaks after upgrade | After upgrading Keycloak the automated realm export fails with a schema mismatch. Users report intermittent login failed errors during the export window. | keycloak,bug,upgrade,sso | Bug | High | Critical | In Progress | EMP008 | 8 | 2026-07-21
EII-106 | Enterprise Identity Integration | SAML assertion clock skew failures for BlueSky Health | BlueSky Health users see intermittent authentication errors caused by SAML assertion timestamp validation. Add clock skew tolerance and better error logging. | saml,sso,authentication,bug | Bug | Medium | Medium | Open | EMP009 | 1 | 2026-06-01
EII-107 | Enterprise Identity Integration | Implement OIDC id token claims mapping | Map group membership claims from the OpenID Connect id token into application roles so downstream services can enforce authorization consistently. | oidc,openid connect,claims,rbac | Feature | Medium | High | In Progress | EMP003 | 8 | 2026-02-16
EII-108 | Enterprise Identity Integration | Rotate expiring PKI certificates | Several service certificates expire next quarter. Rotate certs issued by the internal certificate authority and automate renewal to avoid TLS outages. | pki,certificate,tls,automation | Task | Medium | Medium | Open | EMP009 | 8 | 2026-04-07
EII-109 | Enterprise Identity Integration | OAuth refresh token rotation policy | Implement refresh token rotation with revocation on reuse to harden OAuth flows against token theft. Update client libraries accordingly. | oauth,token,security,hardening | Feature | Medium | High | Open | EMP009 | 8 | 2025-08-17
EII-110 | Enterprise Identity Integration | Okta to Keycloak migration runbook | Document the migration path from Okta to Keycloak for workforce identity, including MFA enrollment, user federation, and rollback procedures in a runbook. | okta,keycloak,migration,runbook | Documentation | Low | Low | In Progress | EMP009 | 3 | 2025-12-12
EII-111 | Enterprise Identity Integration | MFA enrollment for privileged accounts | Require multi-factor authentication for all admin and maintainer roles. Roll out in stages with communication and support documentation. | mfa,security,access,policy | Feature | High | High | Done | EMP005 | 13 | 2026-06-27 | 2026-07-08
EII-112 | Enterprise Identity Integration | RBAC policy audit for production namespaces | Audit role bindings across production namespaces and remove excessive privileges. Several service accounts have cluster-admin that should be scoped down. | rbac,security,kubernetes,audit | Task | High | Critical | Done | EMP008 | 5 | 2026-06-08 | 2026-07-17
EII-113 | Enterprise Identity Integration | SSO login loop after session timeout | Users bounce between the identity provider and the application after session timeout. Reproduce the redirect loop and fix the session cookie configuration. | sso,bug,session,authentication | Bug | Low | Medium | Open | EMP005 | 8 | 2026-01-10
EII-114 | Enterprise Identity Integration | Automate service account credential rotation | Service account credentials are rotated manually today. Automate rotation with the External Secrets Operator and Vault integration to remove the manual process. | eso,vault,secrets,automation | Technical Debt | High | Critical | In Progress | EMP005 | 8 | 2025-10-07
EII-115 | Enterprise Identity Integration | LDAP user federation sync performance | Nightly user federation sync takes four hours. Profile the sync, batch the queries, and cut sync time so access changes propagate faster. | keycloak,performance,ldap,sync | Performance | Medium | High | Done | EMP005 | 3 | 2026-06-07 | 2026-07-02
EII-116 | Enterprise Identity Integration | Standardize authorization error responses | APIs return inconsistent 401 and 403 responses which complicates client handling. Standardize unauthorized and forbidden semantics across services. | api,authorization,standards,refactor | Technical Debt | High | Medium | Open | EMP008 | 8 | 2026-07-21
EII-117 | Enterprise Identity Integration | Keycloak realm export breaks after upgrade (staging) | After upgrading Keycloak the automated realm export fails with a schema mismatch. Users report intermittent login failed errors during the export window. | keycloak,bug,upgrade,sso | Bug | Medium | Medium | Open | EMP005 | 2 | 2026-07-29
EII-118 | Enterprise Identity Integration | SAML assertion clock skew failures for BlueSky Health (staging) | BlueSky Health users see intermittent authentication errors caused by SAML assertion timestamp validation. Add clock skew tolerance and better error logging. | saml,sso,authentication,bug | Bug | Medium | High | Done | EMP005 | 8 | 2026-06-14 | 2026-07-22
EII-119 | Enterprise Identity Integration | Implement OIDC id token claims mapping (staging) | Map group membership claims from the OpenID Connect id token into application roles so downstream services can enforce authorization consistently. | oidc,openid connect,claims,rbac | Feature | Medium | High | Open | EMP005 | 8 | 2026-01-21
EII-120 | Enterprise Identity Integration | Rotate expiring PKI certificates - phase 2 | Several service certificates expire next quarter. Rotate certs issued by the internal certificate authority and automate renewal to avoid TLS outages. | pki,certificate,tls,automation | Task | Medium | Medium | Open | EMP008 | 3 | 2025-10-25
EII-121 | Enterprise Identity Integration | OAuth refresh token rotation policy for EU region | Implement refresh token rotation with revocation on reuse to harden OAuth flows against token theft. Update client libraries accordingly. | oauth,token,security,hardening | Feature | Medium | High | In Progress | EMP005 | 5 | 2025-09-09
EII-122 | Enterprise Identity Integration | Okta to Keycloak migration runbook (production) | Document the migration path from Okta to Keycloak for workforce identity, including MFA enrollment, user federation, and rollback procedures in a runbook. | okta,keycloak,migration,runbook | Documentation | Medium | High | Done | EMP009 | 3 | 2025-12-16 | 2026-01-07
EII-123 | Enterprise Identity Integration | MFA enrollment for privileged accounts (staging) | Require multi-factor authentication for all admin and maintainer roles. Roll out in stages with communication and support documentation. | mfa,security,access,policy | Feature | High | High | In Progress | EMP005 | 8 | 2026-06-28
EII-124 | Enterprise Identity Integration | RBAC policy audit for production namespaces (production) | Audit role bindings across production namespaces and remove excessive privileges. Several service accounts have cluster-admin that should be scoped down. | rbac,security,kubernetes,audit | Task | Low | Medium | Open | EMP003 | 3 | 2025-08-24
EII-125 | Enterprise Identity Integration | SSO login loop after session timeout (production) | Users bounce between the identity provider and the application after session timeout. Reproduce the redirect loop and fix the session cookie configuration. | sso,bug,session,authentication | Bug | High | Medium | In Progress | EMP009 | 8 | 2025-09-02
EII-126 | Enterprise Identity Integration | Automate service account credential rotation follow-up | Service account credentials are rotated manually today. Automate rotation with the External Secrets Operator and Vault integration to remove the manual process. | eso,vault,secrets,automation | Technical Debt | Critical | Critical | Done | EMP005 | 8 | 2026-07-02 | 2026-07-22
EII-127 | Enterprise Identity Integration | LDAP user federation sync performance (production) | Nightly user federation sync takes four hours. Profile the sync, batch the queries, and cut sync time so access changes propagate faster. | keycloak,performance,ldap,sync | Performance | Medium | Low | Done | EMP008 | 3 | 2025-12-02 | 2026-01-07
EII-128 | Enterprise Identity Integration | Standardize authorization error responses (production) | APIs return inconsistent 401 and 403 responses which complicates client handling. Standardize unauthorized and forbidden semantics across services. | api,authorization,standards,refactor | Technical Debt | Low | Low | In Progress | EMP005 | 3 | 2025-09-04
EII-129 | Enterprise Identity Integration | Keycloak realm export breaks after upgrade - phase 2 | After upgrading Keycloak the automated realm export fails with a schema mismatch. Users report intermittent login failed errors during the export window. | keycloak,bug,upgrade,sso | Bug | Low | Low | Open | EMP005 | 1 | 2026-03-26
EII-130 | Enterprise Identity Integration | SAML assertion clock skew failures for BlueSky Health follow-up | BlueSky Health users see intermittent authentication errors caused by SAML assertion timestamp validation. Add clock skew tolerance and better error logging. | saml,sso,authentication,bug | Bug | Medium | Medium | Open | EMP009 | 1 | 2025-10-01
EII-131 | Enterprise Identity Integration | Implement OIDC id token claims mapping for EU region | Map group membership claims from the OpenID Connect id token into application roles so downstream services can enforce authorization consistently. | oidc,openid connect,claims,rbac | Feature | Critical | Critical | Open | EMP005 | 5 | 2026-04-02
EII-132 | Enterprise Identity Integration | Rotate expiring PKI certificates (production) | Several service certificates expire next quarter. Rotate certs issued by the internal certificate authority and automate renewal to avoid TLS outages. | pki,certificate,tls,automation | Task | High | High | In Progress | EMP005 | 3 | 2026-07-22
EII-133 | Enterprise Identity Integration | OAuth refresh token rotation policy - phase 2 | Implement refresh token rotation with revocation on reuse to harden OAuth flows against token theft. Update client libraries accordingly. | oauth,token,security,hardening | Feature | Low | Low | Open | EMP009 | 13 | 2026-06-28
EII-134 | Enterprise Identity Integration | Okta to Keycloak migration runbook follow-up | Document the migration path from Okta to Keycloak for workforce identity, including MFA enrollment, user federation, and rollback procedures in a runbook. | okta,keycloak,migration,runbook | Documentation | High | Medium | In Progress | EMP009 | 2 | 2026-07-10
EII-135 | Enterprise Identity Integration | MFA enrollment for privileged accounts for EU region | Require multi-factor authentication for all admin and maintainer roles. Roll out in stages with communication and support documentation. | mfa,security,access,policy | Feature | Low | Low | Done | EMP008 | 8 | 2025-09-20 | 2025-09-30
EII-136 | Enterprise Identity Integration | RBAC policy audit for production namespaces (staging) | Audit role bindings across production namespaces and remove excessive privileges. Several service accounts have cluster-admin that should be scoped down. | rbac,security,kubernetes,audit | Task | Critical | High | Open | EMP009 | 5 | 2025-12-16
EII-137 | Enterprise Identity Integration | SSO login loop after session timeout for EU region | Users bounce between the identity provider and the application after session timeout. Reproduce the redirect loop and fix the session cookie configuration. | sso,bug,session,authentication | Bug | Medium | High | Review | EMP008 | 8 | 2026-03-17
EII-138 | Enterprise Identity Integration | Automate service account credential rotation (staging) | Service account credentials are rotated manually today. Automate rotation with the External Secrets Operator and Vault integration to remove the manual process. | eso,vault,secrets,automation | Technical Debt | Medium | High | Open | EMP009 | 8 | 2026-06-10
EII-139 | Enterprise Identity Integration | LDAP user federation sync performance - phase 2 | Nightly user federation sync takes four hours. Profile the sync, batch the queries, and cut sync time so access changes propagate faster. | keycloak,performance,ldap,sync | Performance | High | Critical | Done | EMP009 | 3 | 2025-09-08 | 2025-09-29
EII-140 | Enterprise Identity Integration | Standardize authorization error responses (production) | APIs return inconsistent 401 and 403 responses which complicates client handling. Standardize unauthorized and forbidden semantics across services. | api,authorization,standards,refactor | Technical Debt | High | Medium | Done | EMP009 | 8 | 2025-08-27 | 2025-09-17
EII-141 | Enterprise Identity Integration | Keycloak realm export breaks after upgrade (production) | After upgrading Keycloak the automated realm export fails with a schema mismatch. Users report intermittent login failed errors during the export window. | keycloak,bug,upgrade,sso | Bug | Medium | High | In Progress | EMP008 | 1 | 2026-02-13
EII-142 | Enterprise Identity Integration | SAML assertion clock skew failures for BlueSky Health for EU region | BlueSky Health users see intermittent authentication errors caused by SAML assertion timestamp validation. Add clock skew tolerance and better error logging. | saml,sso,authentication,bug | Bug | Medium | High | Open | EMP003 | 5 | 2026-07-07
EII-143 | Enterprise Identity Integration | Implement OIDC id token claims mapping for EU region | Map group membership claims from the OpenID Connect id token into application roles so downstream services can enforce authorization consistently. | oidc,openid connect,claims,rbac | Feature | Critical | Critical | Review | EMP005 | 3 | 2026-06-23
EII-144 | Enterprise Identity Integration | Rotate expiring PKI certificates follow-up | Several service certificates expire next quarter. Rotate certs issued by the internal certificate authority and automate renewal to avoid TLS outages. | pki,certificate,tls,automation | Task | High | Critical | Open | EMP009 | 5 | 2026-01-26
EII-145 | Enterprise Identity Integration | OAuth refresh token rotation policy for EU region | Implement refresh token rotation with revocation on reuse to harden OAuth flows against token theft. Update client libraries accordingly. | oauth,token,security,hardening | Feature | Critical | Critical | Done | EMP009 | 13 | 2025-10-19 | 2026-01-05
EII-146 | Enterprise Identity Integration | Okta to Keycloak migration runbook (production) | Document the migration path from Okta to Keycloak for workforce identity, including MFA enrollment, user federation, and rollback procedures in a runbook. | okta,keycloak,migration,runbook | Documentation | Critical | Critical | Done | EMP009 | 1 | 2025-09-19 | 2025-11-01
EII-147 | Enterprise Identity Integration | MFA enrollment for privileged accounts (staging) | Require multi-factor authentication for all admin and maintainer roles. Roll out in stages with communication and support documentation. | mfa,security,access,policy | Feature | Low | Low | Open | EMP003 | 13 | 2025-08-26
EII-148 | Enterprise Identity Integration | RBAC policy audit for production namespaces - phase 2 | Audit role bindings across production namespaces and remove excessive privileges. Several service accounts have cluster-admin that should be scoped down. | rbac,security,kubernetes,audit | Task | Medium | High | In Progress | EMP003 | 2 | 2026-03-12
CIM-105 | Cloud Infrastructure Modernization | Terraform module refactor for VPC baseline | Split the monolithic Terraform configuration into reusable modules for VPC, subnets, and security groups. Adopt terraform plan checks in the pipeline. | terraform,iac,vpc,refactor | Technical Debt | High | Medium | Done | EMP009 | 8 | 2026-07-13 | 2026-07-19
CIM-106 | Cloud Infrastructure Modernization | Upgrade EKS cluster to next Kubernetes version | Plan and execute the managed cluster upgrade including node group rotation, addon compatibility checks, and workload validation in staging before production. | kubernetes,eks,upgrade,cluster | Task | Low | Medium | Done | EMP004 | 8 | 2026-05-18 | 2026-05-27
CIM-107 | Cloud Infrastructure Modernization | ArgoCD application sync stuck in progressing | Several ArgoCD applications hang in progressing state after a Helm chart update. Investigate the reconciliation loop and fix the health checks. | argocd,gitops,helm,bug | Bug | Medium | Medium | In Progress | EMP006 | 3 | 2025-11-30
CIM-108 | Cloud Infrastructure Modernization | Autoscaling policy for burst workloads | Configure horizontal pod autoscaling and cluster autoscaler policies for burst traffic so throughput scales without manual intervention. | kubernetes,autoscaling,performance,capacity | Feature | High | High | Open | EMP006 | 8 | 2026-03-09
CIM-109 | Cloud Infrastructure Modernization | Migrate ingress to AWS ALB controller | Replace the legacy ingress with the AWS application load balancer controller for better TLS handling and target group management. | alb,ingress,kubernetes,migration | Task | High | Medium | Done | EMP004 | 2 | 2025-10-12 | 2025-10-29
CIM-110 | Cloud Infrastructure Modernization | Loki log retention and index optimization | Log aggregation storage is growing fast. Tune Loki retention, compaction, and index settings to control cost while keeping troubleshooting logs available. | loki,logging,retention,optimization | Performance | Medium | Medium | Open | EMP004 | 5 | 2026-07-07
CIM-111 | Cloud Infrastructure Modernization | Crossplane composition for RDS provisioning | Create a Crossplane composition so teams can provision PostgreSQL RDS instances through Kubernetes CRDs with guardrails instead of manual console work. | crossplane,rds,iac,automation | Feature | Medium | High | Done | EMP009 | 3 | 2026-07-15 | 2026-07-18
CIM-112 | Cloud Infrastructure Modernization | Prometheus alert fatigue reduction | On-call receives too many noisy alerts. Review alertmanager routing and thresholds, delete stale rules, and add runbook links to actionable alerts. | prometheus,alerting,monitoring,oncall | Task | Medium | Low | In Progress | EMP010 | 3 | 2026-05-31
CIM-113 | Cloud Infrastructure Modernization | Terragrunt remote state locking issue | Concurrent applies hit remote state lock contention. Restructure Terragrunt dependencies to reduce blast radius and speed up plans. | terragrunt,terraform,state,bug | Bug | Medium | Medium | In Progress | EMP004 | 2 | 2025-10-11
CIM-114 | Cloud Infrastructure Modernization | Zarf package for air gap deployment | Build a Zarf package so the platform can deploy into a disconnected environment for the federal proof of concept. | zarf,airgap,deployment,packaging | Feature | Critical | Critical | Done | EMP009 | 8 | 2026-05-06 | 2026-05-14
CIM-115 | Cloud Infrastructure Modernization | Helm values standardization across environments | Environment values files have drifted. Standardize values.yaml structure across staging and production and document overrides. | helm,configuration,standards,refactor | Technical Debt | Critical | Critical | Review | EMP010 | 13 | 2026-07-23
CIM-116 | Cloud Infrastructure Modernization | Node disk pressure evictions in production | Pods are evicted under disk pressure on two production nodes. Investigate image garbage collection and ephemeral storage limits for reliability. | kubernetes,reliability,incident,storage | Bug | Medium | Medium | Done | EMP010 | 1 | 2026-05-29 | 2026-06-04
CIM-117 | Cloud Infrastructure Modernization | Terraform module refactor for VPC baseline follow-up | Split the monolithic Terraform configuration into reusable modules for VPC, subnets, and security groups. Adopt terraform plan checks in the pipeline. | terraform,iac,vpc,refactor | Technical Debt | Medium | High | In Progress | EMP004 | 3 | 2025-10-06
CIM-118 | Cloud Infrastructure Modernization | Upgrade EKS cluster to next Kubernetes version - phase 2 | Plan and execute the managed cluster upgrade including node group rotation, addon compatibility checks, and workload validation in staging before production. | kubernetes,eks,upgrade,cluster | Task | High | High | Done | EMP010 | 3 | 2026-05-05 | 2026-06-09
CIM-119 | Cloud Infrastructure Modernization | ArgoCD application sync stuck in progressing (staging) | Several ArgoCD applications hang in progressing state after a Helm chart update. Investigate the reconciliation loop and fix the health checks. | argocd,gitops,helm,bug | Bug | Low | Low | Open | EMP004 | 8 | 2026-05-11
CIM-120 | Cloud Infrastructure Modernization | Autoscaling policy for burst workloads (production) | Configure horizontal pod autoscaling and cluster autoscaler policies for burst traffic so throughput scales without manual intervention. | kubernetes,autoscaling,performance,capacity | Feature | Medium | Medium | Open | EMP010 | 8 | 2026-07-04
CIM-121 | Cloud Infrastructure Modernization | Migrate ingress to AWS ALB controller follow-up | Replace the legacy ingress with the AWS application load balancer controller for better TLS handling and target group management. | alb,ingress,kubernetes,migration | Task | High | High | Done | EMP009 | 5 | 2026-07-09 | 2026-07-26
CIM-122 | Cloud Infrastructure Modernization | Loki log retention and index optimization - phase 2 | Log aggregation storage is growing fast. Tune Loki retention, compaction, and index settings to control cost while keeping troubleshooting logs available. | loki,logging,retention,optimization | Performance | High | High | Done | EMP004 | 5 | 2025-08-06 | 2025-08-10
CIM-123 | Cloud Infrastructure Modernization | Crossplane composition for RDS provisioning follow-up | Create a Crossplane composition so teams can provision PostgreSQL RDS instances through Kubernetes CRDs with guardrails instead of manual console work. | crossplane,rds,iac,automation | Feature | Critical | Critical | Done | EMP006 | 13 | 2025-08-09 | 2025-08-27
CIM-124 | Cloud Infrastructure Modernization | Prometheus alert fatigue reduction (staging) | On-call receives too many noisy alerts. Review alertmanager routing and thresholds, delete stale rules, and add runbook links to actionable alerts. | prometheus,alerting,monitoring,oncall | Task | Low | Low | Done | EMP010 | 2 | 2026-07-13 | 2026-07-20
CIM-125 | Cloud Infrastructure Modernization | Terragrunt remote state locking issue follow-up | Concurrent applies hit remote state lock contention. Restructure Terragrunt dependencies to reduce blast radius and speed up plans. | terragrunt,terraform,state,bug | Bug | Low | Medium | Done | EMP009 | 5 | 2026-05-03 | 2026-06-17
CIM-126 | Cloud Infrastructure Modernization | Zarf package for air gap deployment for EU region | Build a Zarf package so the platform can deploy into a disconnected environment for the federal proof of concept. | zarf,airgap,deployment,packaging | Feature | Low | Low | Open | EMP006 | 8 | 2026-07-19
CIM-127 | Cloud Infrastructure Modernization | Helm values standardization across environments (staging) | Environment values files have drifted. Standardize values.yaml structure across staging and production and document overrides. | helm,configuration,standards,refactor | Technical Debt | Medium | High | Open | EMP010 | 3 | 2025-10-24
CIM-128 | Cloud Infrastructure Modernization | Node disk pressure evictions in production (staging) | Pods are evicted under disk pressure on two production nodes. Investigate image garbage collection and ephemeral storage limits for reliability. | kubernetes,reliability,incident,storage | Bug | Low | Medium | Done | EMP009 | 1 | 2025-11-24 | 2025-12-09
CIM-129 | Cloud Infrastructure Modernization | Terraform module refactor for VPC baseline - phase 2 | Split the monolithic Terraform configuration into reusable modules for VPC, subnets, and security groups. Adopt terraform plan checks in the pipeline. | terraform,iac,vpc,refactor | Technical Debt | Medium | Medium | Open | EMP010 | 8 | 2026-06-07
CIM-130 | Cloud Infrastructure Modernization | Upgrade EKS cluster to next Kubernetes version (production) | Plan and execute the managed cluster upgrade including node group rotation, addon compatibility checks, and workload validation in staging before production. | kubernetes,eks,upgrade,cluster | Task | High | Medium | Review | EMP004 | 3 | 2026-07-13
CIM-131 | Cloud Infrastructure Modernization | ArgoCD application sync stuck in progressing (staging) | Several ArgoCD applications hang in progressing state after a Helm chart update. Investigate the reconciliation loop and fix the health checks. | argocd,gitops,helm,bug | Bug | Critical | Critical | Done | EMP004 | 3 | 2026-06-18 | 2026-07-01
CIM-132 | Cloud Infrastructure Modernization | Autoscaling policy for burst workloads (production) | Configure horizontal pod autoscaling and cluster autoscaler policies for burst traffic so throughput scales without manual intervention. | kubernetes,autoscaling,performance,capacity | Feature | Critical | Critical | Review | EMP006 | 13 | 2026-06-05
CIM-133 | Cloud Infrastructure Modernization | Migrate ingress to AWS ALB controller - phase 2 | Replace the legacy ingress with the AWS application load balancer controller for better TLS handling and target group management. | alb,ingress,kubernetes,migration | Task | Critical | Critical | Review | EMP010 | 3 | 2026-06-25
CIM-134 | Cloud Infrastructure Modernization | Loki log retention and index optimization (production) | Log aggregation storage is growing fast. Tune Loki retention, compaction, and index settings to control cost while keeping troubleshooting logs available. | loki,logging,retention,optimization | Performance | Critical | Critical | In Progress | EMP010 | 3 | 2026-07-04
CIM-135 | Cloud Infrastructure Modernization | Crossplane composition for RDS provisioning (staging) | Create a Crossplane composition so teams can provision PostgreSQL RDS instances through Kubernetes CRDs with guardrails instead of manual console work. | crossplane,rds,iac,automation | Feature | Critical | Critical | In Progress | EMP004 | 5 | 2026-05-24
CIM-136 | Cloud Infrastructure Modernization | Prometheus alert fatigue reduction (staging) | On-call receives too many noisy alerts. Review alertmanager routing and thresholds, delete stale rules, and add runbook links to actionable alerts. | prometheus,alerting,monitoring,oncall | Task | Low | Low | Done | EMP010 | 3 | 2026-05-19 | 2026-06-02
CIM-137 | Cloud Infrastructure Modernization | Terragrunt remote state locking issue follow-up | Concurrent applies hit remote state lock contention. Restructure Terragrunt dependencies to reduce blast radius and speed up plans. | terragrunt,terraform,state,bug | Bug | Medium | Medium | Done | EMP010 | 3 | 2025-12-29 | 2026-01-12
CIM-138 | Cloud Infrastructure Modernization | Zarf package for air gap deployment - phase 2 | Build a Zarf package so the platform can deploy into a disconnected environment for the federal proof of concept. | zarf,airgap,deployment,packaging | Feature | Medium | Medium | Done | EMP004 | 8 | 2026-06-17 | 2026-06-23
CIM-139 | Cloud Infrastructure Modernization | Helm values standardization across environments for EU region | Environment values files have drifted. Standardize values.yaml structure across staging and production and document overrides. | helm,configuration,standards,refactor | Technical Debt | Low | Medium | In Progress | EMP009 | 13 | 2025-11-18
CIM-140 | Cloud Infrastructure Modernization | Node disk pressure evictions in production (staging) | Pods are evicted under disk pressure on two production nodes. Investigate image garbage collection and ephemeral storage limits for reliability. | kubernetes,reliability,incident,storage | Bug | Medium | Low | Done | EMP010 | 5 | 2026-05-28 | 2026-06-07
CIM-141 | Cloud Infrastructure Modernization | Terraform module refactor for VPC baseline (staging) | Split the monolithic Terraform configuration into reusable modules for VPC, subnets, and security groups. Adopt terraform plan checks in the pipeline. | terraform,iac,vpc,refactor | Technical Debt | Low | Low | Review | EMP009 | 13 | 2026-07-26
CIM-142 | Cloud Infrastructure Modernization | Upgrade EKS cluster to next Kubernetes version for EU region | Plan and execute the managed cluster upgrade including node group rotation, addon compatibility checks, and workload validation in staging before production. | kubernetes,eks,upgrade,cluster | Task | High | High | Done | EMP009 | 5 | 2026-04-12 | 2026-04-23
CIM-143 | Cloud Infrastructure Modernization | ArgoCD application sync stuck in progressing - phase 2 | Several ArgoCD applications hang in progressing state after a Helm chart update. Investigate the reconciliation loop and fix the health checks. | argocd,gitops,helm,bug | Bug | Low | Low | In Progress | EMP004 | 3 | 2026-04-06
CIM-144 | Cloud Infrastructure Modernization | Autoscaling policy for burst workloads (staging) | Configure horizontal pod autoscaling and cluster autoscaler policies for burst traffic so throughput scales without manual intervention. | kubernetes,autoscaling,performance,capacity | Feature | Low | Low | Done | EMP006 | 5 | 2026-02-15 | 2026-02-27
SAC-105 | Secure Application Compliance | Triage critical CVEs from NeuVector scan | The latest container security scan flagged critical vulnerabilities in three base images. Patch, rebuild, and redeploy affected services. | neuvector,cve,vulnerability,containers | Bug | Medium | Low | Open | EMP009 | 5 | 2026-06-19
SAC-106 | Secure Application Compliance | SonarQube quality gate for merge requests | Enforce static code analysis quality gates on every merge request so new code cannot introduce critical code smells or security hotspots. | sonarqube,quality,ci,security | Feature | High | High | Done | EMP005 | 5 | 2026-07-04 | 2026-07-28
SAC-107 | Secure Application Compliance | Kyverno policy to block privileged pods | Add an admission control policy that blocks privileged containers and enforces read-only root filesystems in production namespaces. | kyverno,policy,kubernetes,hardening | Feature | High | High | Done | EMP009 | 13 | 2026-05-13 | 2026-05-28
SAC-108 | Secure Application Compliance | Secrets sprawl cleanup with External Secrets Operator | Secrets are duplicated across namespaces and CI variables. Consolidate into Vault with the External Secrets Operator and rotate exposed credentials. | eso,vault,secrets,cleanup | Technical Debt | Medium | High | Open | EMP009 | 8 | 2026-01-01
SAC-109 | Secure Application Compliance | Quarterly compliance evidence automation | Collecting audit evidence is a manual process each quarter. Automate report generation for access reviews and scan results. | compliance,automation,audit,reporting | Feature | Low | Low | Open | EMP010 | 8 | 2026-06-01
SAC-110 | Secure Application Compliance | Penetration test finding: verbose error pages | The pen test found stack traces leaking in error responses. Sanitize error handling and add security headers across public endpoints. | security,pentest,hardening,bug | Bug | Low | Low | In Progress | EMP010 | 3 | 2025-08-18
SAC-111 | Secure Application Compliance | Dependency scanning in GitLab pipeline | Add dependency and license scanning stages to the GitLab CI/CD pipeline with severity thresholds that fail the build. | gitlab,ci,scanning,dependencies | Feature | Medium | Low | In Progress | EMP005 | 3 | 2025-10-24
SAC-112 | Secure Application Compliance | Image signing and verification rollout | Sign build artifacts and verify signatures at admission so only trusted images run in the cluster. | supply-chain,signing,kubernetes,policy | Feature | Medium | Low | Done | EMP005 | 3 | 2025-12-14 | 2025-12-26
SAC-113 | Secure Application Compliance | Vulnerability SLA dashboard | Track remediation SLAs for open vulnerabilities by severity in a Grafana dashboard backed by scan exports. | vulnerability,sla,dashboard,reporting | Feature | Medium | High | Done | EMP005 | 3 | 2026-06-14 | 2026-07-11
SAC-114 | Secure Application Compliance | Harden PostgreSQL authentication configuration | Move database access to IAM authentication where possible, enforce TLS, and remove shared credentials from application configs. | postgres,iam,tls,hardening | Task | Medium | Medium | Open | EMP009 | 2 | 2026-06-01
SAC-115 | Secure Application Compliance | Triage critical CVEs from NeuVector scan for EU region | The latest container security scan flagged critical vulnerabilities in three base images. Patch, rebuild, and redeploy affected services. | neuvector,cve,vulnerability,containers | Bug | Medium | Medium | Review | EMP005 | 3 | 2026-07-12
SAC-116 | Secure Application Compliance | SonarQube quality gate for merge requests (production) | Enforce static code analysis quality gates on every merge request so new code cannot introduce critical code smells or security hotspots. | sonarqube,quality,ci,security | Feature | High | High | Done | EMP009 | 8 | 2025-09-10 | 2025-10-08
SAC-117 | Secure Application Compliance | Kyverno policy to block privileged pods follow-up | Add an admission control policy that blocks privileged containers and enforces read-only root filesystems in production namespaces. | kyverno,policy,kubernetes,hardening | Feature | High | Medium | Done | EMP010 | 8 | 2026-06-16 | 2026-06-23
SAC-118 | Secure Application Compliance | Secrets sprawl cleanup with External Secrets Operator follow-up | Secrets are duplicated across namespaces and CI variables. Consolidate into Vault with the External Secrets Operator and rotate exposed credentials. | eso,vault,secrets,cleanup | Technical Debt | Medium | High | In Progress | EMP009 | 8 | 2026-06-12
SAC-119 | Secure Application Compliance | Quarterly compliance evidence automation - phase 2 | Collecting audit evidence is a manual process each quarter. Automate report generation for access reviews and scan results. | compliance,automation,audit,reporting | Feature | Medium | Medium | In Progress | EMP005 | 13 | 2026-03-10
SAC-120 | Secure Application Compliance | Penetration test finding: verbose error pages - phase 2 | The pen test found stack traces leaking in error responses. Sanitize error handling and add security headers across public endpoints. | security,pentest,hardening,bug | Bug | Medium | High | Open | EMP009 | 8 | 2026-01-29
SAC-121 | Secure Application Compliance | Dependency scanning in GitLab pipeline (staging) | Add dependency and license scanning stages to the GitLab CI/CD pipeline with severity thresholds that fail the build. | gitlab,ci,scanning,dependencies | Feature | High | High | Done | EMP010 | 3 | 2026-06-22 | 2026-06-24
SAC-122 | Secure Application Compliance | Image signing and verification rollout - phase 2 | Sign build artifacts and verify signatures at admission so only trusted images run in the cluster. | supply-chain,signing,kubernetes,policy | Feature | High | Critical | Done | EMP009 | 8 | 2025-10-17 | 2025-10-21
SAC-123 | Secure Application Compliance | Vulnerability SLA dashboard (staging) | Track remediation SLAs for open vulnerabilities by severity in a Grafana dashboard backed by scan exports. | vulnerability,sla,dashboard,reporting | Feature | Medium | High | In Progress | EMP005 | 8 | 2026-01-30
SAC-124 | Secure Application Compliance | Harden PostgreSQL authentication configuration - phase 2 | Move database access to IAM authentication where possible, enforce TLS, and remove shared credentials from application configs. | postgres,iam,tls,hardening | Task | Medium | High | In Progress | EMP010 | 5 | 2026-02-06
SAC-125 | Secure Application Compliance | Triage critical CVEs from NeuVector scan - phase 2 | The latest container security scan flagged critical vulnerabilities in three base images. Patch, rebuild, and redeploy affected services. | neuvector,cve,vulnerability,containers | Bug | Low | Low | Done | EMP009 | 8 | 2026-04-03 | 2026-04-23
SAC-126 | Secure Application Compliance | SonarQube quality gate for merge requests (staging) | Enforce static code analysis quality gates on every merge request so new code cannot introduce critical code smells or security hotspots. | sonarqube,quality,ci,security | Feature | Critical | High | In Progress | EMP009 | 8 | 2026-07-23
SAC-127 | Secure Application Compliance | Kyverno policy to block privileged pods for EU region | Add an admission control policy that blocks privileged containers and enforces read-only root filesystems in production namespaces. | kyverno,policy,kubernetes,hardening | Feature | Medium | High | Done | EMP005 | 3 | 2025-08-04 | 2025-08-19
SAC-128 | Secure Application Compliance | Secrets sprawl cleanup with External Secrets Operator (production) | Secrets are duplicated across namespaces and CI variables. Consolidate into Vault with the External Secrets Operator and rotate exposed credentials. | eso,vault,secrets,cleanup | Technical Debt | High | High | Done | EMP005 | 8 | 2025-09-16 | 2025-10-11
SAC-129 | Secure Application Compliance | Quarterly compliance evidence automation (production) | Collecting audit evidence is a manual process each quarter. Automate report generation for access reviews and scan results. | compliance,automation,audit,reporting | Feature | Low | Low | In Progress | EMP009 | 13 | 2026-03-19
SAC-130 | Secure Application Compliance | Penetration test finding: verbose error pages (staging) | The pen test found stack traces leaking in error responses. Sanitize error handling and add security headers across public endpoints. | security,pentest,hardening,bug | Bug | Medium | Low | Open | EMP005 | 2 | 2026-02-02
SAC-131 | Secure Application Compliance | Dependency scanning in GitLab pipeline (production) | Add dependency and license scanning stages to the GitLab CI/CD pipeline with severity thresholds that fail the build. | gitlab,ci,scanning,dependencies | Feature | High | High | Done | EMP010 | 5 | 2025-10-26 | 2025-11-04
SAC-132 | Secure Application Compliance | Image signing and verification rollout follow-up | Sign build artifacts and verify signatures at admission so only trusted images run in the cluster. | supply-chain,signing,kubernetes,policy | Feature | High | High | Done | EMP010 | 8 | 2025-08-11 | 2025-09-01
SAC-133 | Secure Application Compliance | Vulnerability SLA dashboard (staging) | Track remediation SLAs for open vulnerabilities by severity in a Grafana dashboard backed by scan exports. | vulnerability,sla,dashboard,reporting | Feature | Medium | Low | Done | EMP009 | 5 | 2026-07-03 | 2026-07-27
SAC-134 | Secure Application Compliance | Harden PostgreSQL authentication configuration (production) | Move database access to IAM authentication where possible, enforce TLS, and remove shared credentials from application configs. | postgres,iam,tls,hardening | Task | Medium | Medium | Done | EMP009 | 5 | 2026-02-13 | 2026-04-04
SAC-135 | Secure Application Compliance | Triage critical CVEs from NeuVector scan (staging) | The latest container security scan flagged critical vulnerabilities in three base images. Patch, rebuild, and redeploy affected services. | neuvector,cve,vulnerability,containers | Bug | Critical | High | Open | EMP010 | 3 | 2025-10-01
SAC-136 | Secure Application Compliance | SonarQube quality gate for merge requests follow-up | Enforce static code analysis quality gates on every merge request so new code cannot introduce critical code smells or security hotspots. | sonarqube,quality,ci,security | Feature | High | Critical | Done | EMP009 | 5 | 2025-10-07 | 2025-10-17
SAC-137 | Secure Application Compliance | Kyverno policy to block privileged pods - phase 2 | Add an admission control policy that blocks privileged containers and enforces read-only root filesystems in production namespaces. | kyverno,policy,kubernetes,hardening | Feature | Medium | Low | Done | EMP010 | 8 | 2026-06-14 | 2026-06-19
SAC-138 | Secure Application Compliance | Secrets sprawl cleanup with External Secrets Operator (production) | Secrets are duplicated across namespaces and CI variables. Consolidate into Vault with the External Secrets Operator and rotate exposed credentials. | eso,vault,secrets,cleanup | Technical Debt | High | Critical | In Progress | EMP005 | 13 | 2026-02-10
EPA-105 | Executive Portfolio Analytics | Add drill-down to team velocity dashboard | Executives want to click from the team velocity dashboard into the underlying issue detail. Add Grafana data links and a detail table panel backed by a PostgreSQL view. | grafana,dashboard,postgres,drill-down | Feature | Low | Low | Review | EMP005 | 5 | 2026-07-20
EPA-106 | Executive Portfolio Analytics | Optimize slow PostgreSQL query behind team velocity panel | The team velocity panel takes over 8 seconds to render. Query plan shows a sequential scan; add indexes and rewrite the aggregation to improve response time and reduce latency. | postgres,performance,query,index | Performance | Medium | Medium | In Progress | EMP004 | 5 | 2026-05-09
EPA-107 | Executive Portfolio Analytics | Dashboard variables reset after time range change | Selecting a new time range clears the customer and project filter variables. Users lose their filter state and must reselect. Investigate Grafana variable persistence. | grafana,bug,filters,dashboard | Bug | Medium | Low | Done | EMP007 | 3 | 2026-06-10 | 2026-06-20
EPA-108 | Executive Portfolio Analytics | Add Prometheus metrics for ETL pipeline | Instrument the workbook import and GitHub sync with Prometheus metrics so we can monitor load duration, record counts, and failures in Grafana with alerting. | prometheus,metrics,monitoring,etl | Feature | Medium | Medium | Open | EMP006 | 5 | 2025-10-13
EPA-109 | Executive Portfolio Analytics | Scheduled PDF export of executive dashboard | Leadership wants a weekly PDF export of the executive dashboard emailed automatically. Evaluate Grafana reporting options and schedule generation via cron automation. | grafana,pdf,report,automation | Feature | Medium | Medium | Done | EMP005 | 8 | 2026-05-28 | 2026-06-14
EPA-110 | Executive Portfolio Analytics | Cache expensive aggregation queries with Redis | Repeated dashboard loads re-run heavy aggregations. Introduce a Redis cache for pre-computed rollups to improve dashboard response time. | redis,cache,performance,postgres | Performance | Medium | Medium | Review | EMP006 | 8 | 2025-11-30
EPA-111 | Executive Portfolio Analytics | Row-level security for customer-scoped dashboards | Customer success engineers should only see dashboards for their assigned customers. Implement role-based access with RBAC policies and PostgreSQL row filters. | rbac,security,postgres,grafana | Feature | Medium | Low | Open | EMP007 | 13 | 2026-06-08
EPA-112 | Executive Portfolio Analytics | Refactor legacy KPI SQL views | The original KPI views contain duplicated logic and outdated column names. Refactor into layered views with consistent naming to reduce technical debt. | postgres,refactor,technical-debt,views | Technical Debt | Medium | Medium | Review | EMP005 | 13 | 2026-05-25
EPA-113 | Executive Portfolio Analytics | Sprint velocity trend widget | Add a panel showing weekly completed weight per team so managers can track velocity trends and spot delivery slowdowns early. | grafana,velocity,metrics,dashboard | Feature | Critical | High | Done | EMP007 | 3 | 2026-06-05 | 2026-06-08
EPA-114 | Executive Portfolio Analytics | Fix timezone drift in created_date reporting | Issues created late in the evening appear under the wrong day in dashboards. Normalize timestamps to UTC in the ETL and cast to date at query time. | bug,timezone,etl,postgres | Bug | Medium | Medium | Done | EMP006 | 5 | 2026-05-08 | 2026-05-17
EPA-115 | Executive Portfolio Analytics | AI executive summary panel formatting | The AI-generated executive summary renders raw markdown in the panel. Improve the rendering, and add loading and error states for the AI analytics endpoint. | ai,llm,dashboard,markdown | Bug | Medium | Low | Open | EMP007 | 5 | 2026-06-23
EPA-116 | Executive Portfolio Analytics | Alerting on stale data imports | If the nightly import fails silently the dashboards show stale data. Add freshness metrics and Grafana alerting when the last successful load is older than 24 hours. | alerting,monitoring,etl,grafana | Feature | Medium | Low | Review | EMP006 | 3 | 2025-10-20
EPA-117 | Executive Portfolio Analytics | Add drill-down to team velocity dashboard - phase 2 | Executives want to click from the team velocity dashboard into the underlying issue detail. Add Grafana data links and a detail table panel backed by a PostgreSQL view. | grafana,dashboard,postgres,drill-down | Feature | Critical | Critical | Open | EMP005 | 5 | 2025-12-22
EPA-118 | Executive Portfolio Analytics | Optimize slow PostgreSQL query behind risk overview panel - phase 2 | The risk overview panel takes over 8 seconds to render. Query plan shows a sequential scan; add indexes and rewrite the aggregation to improve response time and reduce latency. | postgres,performance,query,index | Performance | Medium | Medium | Done | EMP004 | 3 | 2025-12-31 | 2026-01-15
EPA-119 | Executive Portfolio Analytics | Dashboard variables reset after time range change for EU region | Selecting a new time range clears the customer and project filter variables. Users lose their filter state and must reselect. Investigate Grafana variable persistence. | grafana,bug,filters,dashboard | Bug | High | High | Open | EMP007 | 8 | 2026-04-30
EPA-120 | Executive Portfolio Analytics | Add Prometheus metrics for ETL pipeline for EU region | Instrument the workbook import and GitHub sync with Prometheus metrics so we can monitor load duration, record counts, and failures in Grafana with alerting. | prometheus,metrics,monitoring,etl | Feature | Medium | Low | Open | EMP005 | 5 | 2026-07-24
EPA-121 | Executive Portfolio Analytics | Scheduled PDF export of executive dashboard (staging) | Leadership wants a weekly PDF export of the executive dashboard emailed automatically. Evaluate Grafana reporting options and schedule generation via cron automation. | grafana,pdf,report,automation | Feature | Medium | High | Review | EMP007 | 5 | 2026-04-14
EPA-122 | Executive Portfolio Analytics | Cache expensive aggregation queries with Redis - phase 2 | Repeated dashboard loads re-run heavy aggregations. Introduce a Redis cache for pre-computed rollups to improve dashboard response time. | redis,cache,performance,postgres | Performance | Medium | Low | Done | EMP007 | 3 | 2025-11-12 | 2025-11-23
EPA-123 | Executive Portfolio Analytics | Row-level security for customer-scoped dashboards (production) | Customer success engineers should only see dashboards for their assigned customers. Implement role-based access with RBAC policies and PostgreSQL row filters. | rbac,security,postgres,grafana | Feature | Medium | Medium | Open | EMP006 | 13 | 2026-06-29
EPA-124 | Executive Portfolio Analytics | Refactor legacy KPI SQL views follow-up | The original KPI views contain duplicated logic and outdated column names. Refactor into layered views with consistent naming to reduce technical debt. | postgres,refactor,technical-debt,views | Technical Debt | Medium | Medium | In Progress | EMP004 | 13 | 2025-10-07
EPA-125 | Executive Portfolio Analytics | Sprint velocity trend widget (staging) | Add a panel showing weekly completed weight per team so managers can track velocity trends and spot delivery slowdowns early. | grafana,velocity,metrics,dashboard | Feature | High | Critical | Done | EMP006 | 5 | 2026-04-29 | 2026-05-05
EPA-126 | Executive Portfolio Analytics | Fix timezone drift in created_date reporting follow-up | Issues created late in the evening appear under the wrong day in dashboards. Normalize timestamps to UTC in the ETL and cast to date at query time. | bug,timezone,etl,postgres | Bug | Critical | Critical | Done | EMP006 | 8 | 2026-05-07 | 2026-05-14
EPA-127 | Executive Portfolio Analytics | AI executive summary panel formatting (staging) | The AI-generated executive summary renders raw markdown in the panel. Improve the rendering, and add loading and error states for the AI analytics endpoint. | ai,llm,dashboard,markdown | Bug | Medium | Low | Done | EMP005 | 5 | 2026-07-14 | 2026-07-23
EPA-128 | Executive Portfolio Analytics | Alerting on stale data imports follow-up | If the nightly import fails silently the dashboards show stale data. Add freshness metrics and Grafana alerting when the last successful load is older than 24 hours. | alerting,monitoring,etl,grafana | Feature | Medium | High | Open | EMP004 | 8 | 2026-03-24
EPA-129 | Executive Portfolio Analytics | Add drill-down to risk overview dashboard follow-up | Executives want to click from the risk overview dashboard into the underlying issue detail. Add Grafana data links and a detail table panel backed by a PostgreSQL view. | grafana,dashboard,postgres,drill-down | Feature | Critical | Critical | Done | EMP007 | 5 | 2026-05-26 | 2026-06-14
EPA-130 | Executive Portfolio Analytics | Optimize slow PostgreSQL query behind portfolio health panel for EU region | The portfolio health panel takes over 8 seconds to render. Query plan shows a sequential scan; add indexes and rewrite the aggregation to improve response time and reduce latency. | postgres,performance,query,index | Performance | High | Critical | Review | EMP006 | 3 | 2025-11-26
EPA-131 | Executive Portfolio Analytics | Dashboard variables reset after time range change (production) | Selecting a new time range clears the customer and project filter variables. Users lose their filter state and must reselect. Investigate Grafana variable persistence. | grafana,bug,filters,dashboard | Bug | Medium | High | Open | EMP007 | 3 | 2026-04-02
EPA-132 | Executive Portfolio Analytics | Add Prometheus metrics for ETL pipeline - phase 2 | Instrument the workbook import and GitHub sync with Prometheus metrics so we can monitor load duration, record counts, and failures in Grafana with alerting. | prometheus,metrics,monitoring,etl | Feature | Medium | High | Done | EMP005 | 5 | 2025-10-19 | 2025-11-05
EPA-133 | Executive Portfolio Analytics | Scheduled PDF export of executive dashboard - phase 2 | Leadership wants a weekly PDF export of the executive dashboard emailed automatically. Evaluate Grafana reporting options and schedule generation via cron automation. | grafana,pdf,report,automation | Feature | Critical | Critical | Open | EMP006 | 8 | 2026-07-03
EPA-134 | Executive Portfolio Analytics | Cache expensive aggregation queries with Redis follow-up | Repeated dashboard loads re-run heavy aggregations. Introduce a Redis cache for pre-computed rollups to improve dashboard response time. | redis,cache,performance,postgres | Performance | Low | Low | Done | EMP004 | 5 | 2026-07-12 | 2026-07-21
CAP-104 | Customer Administration Portal | Customer search returns stale results | Newly onboarded customers do not appear in search until the next day. Fix the indexing job so search reflects changes within minutes. | search,bug,indexing,portal | Bug | Medium | Medium | Done | EMP003 | 3 | 2026-04-08 | 2026-04-10
CAP-105 | Customer Administration Portal | Self-service account provisioning workflow | Allow customer admins to provision user accounts with approval workflow, removing the manual onboarding queue. | provisioning,workflow,automation,portal | Feature | Medium | Medium | Done | EMP010 | 13 | 2025-11-19 | 2025-11-24
CAP-106 | Customer Administration Portal | Audit trail export to CSV | Compliance teams need to export the customer audit trail with filters applied. Add CSV export with background generation for large ranges. | audit,export,csv,compliance | Feature | Medium | High | Review | EMP010 | 8 | 2025-11-07
CAP-107 | Customer Administration Portal | License usage meter accuracy | Reported license usage differs from billing records. Reconcile the counting logic and add tests around edge cases. | licensing,bug,billing,accuracy | Bug | Low | Low | Done | EMP006 | 3 | 2026-05-24 | 2026-06-02
CAP-108 | Customer Administration Portal | Bulk user import validation | Bulk CSV imports fail silently on malformed rows. Validate input, report row-level errors, and support partial retries. | import,validation,csv,portal | Bug | Low | Medium | Done | EMP006 | 5 | 2026-06-30 | 2026-07-04
CAP-109 | Customer Administration Portal | Portal session handling behind load balancer | Sessions drop when traffic shifts between instances. Fix sticky session and cookie configuration behind the load balancer. | session,alb,bug,reliability | Bug | Medium | Medium | Done | EMP010 | 3 | 2026-05-15 | 2026-05-24
CAP-110 | Customer Administration Portal | Accessibility pass for admin screens | Bring the admin screens to WCAG AA: keyboard navigation, contrast, and screen reader labels for form controls. | accessibility,ui,frontend,quality | Task | Low | Low | Review | EMP003 | 3 | 2026-07-30
CAP-111 | Customer Administration Portal | Notification preferences per customer | Customers want control over which lifecycle emails they receive. Add notification preference management with sensible defaults. | notifications,feature,portal,email | Feature | Medium | High | Done | EMP010 | 5 | 2025-12-09 | 2025-12-14
CAP-112 | Customer Administration Portal | Migrate portal database to managed RDS | Move the self-hosted PostgreSQL database to Amazon RDS with minimal downtime, including replication cutover and backup validation. | rds,postgres,migration,database | Task | Low | Low | Done | EMP003 | 3 | 2026-06-09 | 2026-06-15
CAP-113 | Customer Administration Portal | Customer search returns stale results (production) | Newly onboarded customers do not appear in search until the next day. Fix the indexing job so search reflects changes within minutes. | search,bug,indexing,portal | Bug | Medium | High | Done | EMP006 | 5 | 2025-11-11 | 2025-11-17
CAP-114 | Customer Administration Portal | Self-service account provisioning workflow (production) | Allow customer admins to provision user accounts with approval workflow, removing the manual onboarding queue. | provisioning,workflow,automation,portal | Feature | Low | Low | Done | EMP003 | 8 | 2026-04-02 | 2026-04-07
CAP-115 | Customer Administration Portal | Audit trail export to CSV for EU region | Compliance teams need to export the customer audit trail with filters applied. Add CSV export with background generation for large ranges. | audit,export,csv,compliance | Feature | Low | Medium | Done | EMP003 | 8 | 2026-05-24 | 2026-06-07
CAP-116 | Customer Administration Portal | License usage meter accuracy follow-up | Reported license usage differs from billing records. Reconcile the counting logic and add tests around edge cases. | licensing,bug,billing,accuracy | Bug | High | Medium | Done | EMP010 | 3 | 2026-06-11 | 2026-06-22
CAP-117 | Customer Administration Portal | Bulk user import validation - phase 2 | Bulk CSV imports fail silently on malformed rows. Validate input, report row-level errors, and support partial retries. | import,validation,csv,portal | Bug | Medium | Medium | Done | EMP006 | 1 | 2026-06-13 | 2026-06-15
CAP-118 | Customer Administration Portal | Portal session handling behind load balancer (staging) | Sessions drop when traffic shifts between instances. Fix sticky session and cookie configuration behind the load balancer. | session,alb,bug,reliability | Bug | Medium | Medium | Done | EMP003 | 2 | 2025-09-01 | 2025-09-05
CAP-119 | Customer Administration Portal | Accessibility pass for admin screens (staging) | Bring the admin screens to WCAG AA: keyboard navigation, contrast, and screen reader labels for form controls. | accessibility,ui,frontend,quality | Task | Medium | High | Done | EMP006 | 2 | 2026-05-20 | 2026-05-30
CAP-120 | Customer Administration Portal | Notification preferences per customer (production) | Customers want control over which lifecycle emails they receive. Add notification preference management with sensible defaults. | notifications,feature,portal,email | Feature | Medium | Low | In Progress | EMP010 | 3 | 2026-07-02
CAP-121 | Customer Administration Portal | Migrate portal database to managed RDS follow-up | Move the self-hosted PostgreSQL database to Amazon RDS with minimal downtime, including replication cutover and backup validation. | rds,postgres,migration,database | Task | Medium | Medium | Done | EMP003 | 8 | 2026-06-04 | 2026-06-08
CAP-122 | Customer Administration Portal | Customer search returns stale results - phase 2 | Newly onboarded customers do not appear in search until the next day. Fix the indexing job so search reflects changes within minutes. | search,bug,indexing,portal | Bug | Medium | Medium | Done | EMP006 | 3 | 2026-05-11 | 2026-05-14
CAP-123 | Customer Administration Portal | Self-service account provisioning workflow - phase 2 | Allow customer admins to provision user accounts with approval workflow, removing the manual onboarding queue. | provisioning,workflow,automation,portal | Feature | Medium | Medium | Done | EMP010 | 3 | 2026-06-04 | 2026-06-08
CAP-124 | Customer Administration Portal | Audit trail export to CSV follow-up | Compliance teams need to export the customer audit trail with filters applied. Add CSV export with background generation for large ranges. | audit,export,csv,compliance | Feature | Medium | High | Open | EMP010 | 3 | 2026-06-12
CAP-125 | Customer Administration Portal | License usage meter accuracy (production) | Reported license usage differs from billing records. Reconcile the counting logic and add tests around edge cases. | licensing,bug,billing,accuracy | Bug | Medium | Medium | Done | EMP003 | 3 | 2026-05-29 | 2026-06-01
CAP-126 | Customer Administration Portal | Bulk user import validation - phase 2 | Bulk CSV imports fail silently on malformed rows. Validate input, report row-level errors, and support partial retries. | import,validation,csv,portal | Bug | Low | Medium | Done | EMP006 | 5 | 2026-07-18 | 2026-07-21
CAP-127 | Customer Administration Portal | Portal session handling behind load balancer for EU region | Sessions drop when traffic shifts between instances. Fix sticky session and cookie configuration behind the load balancer. | session,alb,bug,reliability | Bug | Medium | Low | Done | EMP010 | 3 | 2026-01-20 | 2026-01-22
CAP-128 | Customer Administration Portal | Accessibility pass for admin screens for EU region | Bring the admin screens to WCAG AA: keyboard navigation, contrast, and screen reader labels for form controls. | accessibility,ui,frontend,quality | Task | Medium | Low | Done | EMP003 | 5 | 2026-06-11 | 2026-06-21
CAP-129 | Customer Administration Portal | Notification preferences per customer follow-up | Customers want control over which lifecycle emails they receive. Add notification preference management with sensible defaults. | notifications,feature,portal,email | Feature | Critical | Critical | Open | EMP006 | 13 | 2026-06-24
CCO-104 | Cloud Cost Optimization | Rightsize overprovisioned EC2 instances | Utilization data shows several instances under 15 percent CPU. Rightsize instance types and document the review cadence. | ec2,cost,rightsizing,aws | Task | Medium | Medium | Open | EMP009 | 3 | 2026-06-07
CCO-105 | Cloud Cost Optimization | Idle resource detection automation | Detect unattached volumes, idle load balancers, and stopped instances with a scheduled job and report candidates for cleanup. | automation,cost,cleanup,aws | Feature | Low | Medium | In Progress | EMP004 | 8 | 2025-09-30
CCO-106 | Cloud Cost Optimization | S3 lifecycle policies for log archives | Move aging log archives to infrequent access and glacier tiers with lifecycle policies to cut object storage spend. | s3,lifecycle,storage,cost | Task | Medium | Medium | Done | EMP005 | 3 | 2026-06-16 | 2026-06-27
CCO-107 | Cloud Cost Optimization | Reserved instance and savings plan analysis | Analyze steady-state compute usage and recommend reserved instance or savings plan purchases with projected savings. | cost,analysis,aws,finance | Task | Medium | High | Done | EMP004 | 2 | 2026-06-28 | 2026-07-13
CCO-108 | Cloud Cost Optimization | Cost allocation tagging enforcement | Enforce required cost allocation tags via policy so spend can be attributed to teams and customers accurately. | tagging,policy,cost,governance | Feature | Low | Medium | Done | EMP004 | 8 | 2026-07-12 | 2026-07-16
CCO-109 | Cloud Cost Optimization | Grafana cost dashboard per team | Build a dashboard showing spend by team, service, and environment with month over month trend and budget thresholds. | grafana,dashboard,cost,reporting | Feature | Low | Low | Done | EMP009 | 8 | 2026-06-04 | 2026-06-05
CCO-110 | Cloud Cost Optimization | ElastiCache cluster consolidation | Multiple underutilized Redis clusters can be consolidated. Plan migration with cache key namespace isolation. | elasticache,redis,consolidation,cost | Task | High | High | Done | EMP005 | 5 | 2026-07-11 | 2026-07-19
CCO-111 | Cloud Cost Optimization | Kubernetes requests and limits tuning | Overstated resource requests cause poor bin packing and wasted nodes. Tune requests from usage data to reduce cluster cost. | kubernetes,capacity,cost,tuning | Performance | Critical | Critical | Review | EMP005 | 8 | 2026-05-14
CCO-112 | Cloud Cost Optimization | Anomaly alerts on daily spend | Alert when daily spend deviates from forecast so surprises are caught within a day instead of at invoice time. | alerting,cost,anomaly,monitoring | Feature | Medium | Medium | Open | EMP009 | 5 | 2026-03-31
CCO-113 | Cloud Cost Optimization | Rightsize overprovisioned EC2 instances (production) | Utilization data shows several instances under 15 percent CPU. Rightsize instance types and document the review cadence. | ec2,cost,rightsizing,aws | Task | Medium | High | Review | EMP005 | 5 | 2025-11-23
CCO-114 | Cloud Cost Optimization | Idle resource detection automation - phase 2 | Detect unattached volumes, idle load balancers, and stopped instances with a scheduled job and report candidates for cleanup. | automation,cost,cleanup,aws | Feature | Low | Medium | Open | EMP005 | 5 | 2025-12-01
CCO-115 | Cloud Cost Optimization | S3 lifecycle policies for log archives - phase 2 | Move aging log archives to infrequent access and glacier tiers with lifecycle policies to cut object storage spend. | s3,lifecycle,storage,cost | Task | High | High | Review | EMP005 | 3 | 2026-07-13
CCO-116 | Cloud Cost Optimization | Reserved instance and savings plan analysis follow-up | Analyze steady-state compute usage and recommend reserved instance or savings plan purchases with projected savings. | cost,analysis,aws,finance | Task | Medium | High | Open | EMP005 | 8 | 2026-05-10
CCO-117 | Cloud Cost Optimization | Cost allocation tagging enforcement for EU region | Enforce required cost allocation tags via policy so spend can be attributed to teams and customers accurately. | tagging,policy,cost,governance | Feature | High | Medium | Review | EMP004 | 8 | 2026-06-16
CCO-118 | Cloud Cost Optimization | Grafana cost dashboard per team for EU region | Build a dashboard showing spend by team, service, and environment with month over month trend and budget thresholds. | grafana,dashboard,cost,reporting | Feature | Low | Low | Open | EMP005 | 13 | 2026-06-05
CCO-119 | Cloud Cost Optimization | ElastiCache cluster consolidation (production) | Multiple underutilized Redis clusters can be consolidated. Plan migration with cache key namespace isolation. | elasticache,redis,consolidation,cost | Task | High | High | Review | EMP005 | 5 | 2026-06-03
CCO-120 | Cloud Cost Optimization | Kubernetes requests and limits tuning (staging) | Overstated resource requests cause poor bin packing and wasted nodes. Tune requests from usage data to reduce cluster cost. | kubernetes,capacity,cost,tuning | Performance | Medium | Low | Review | EMP004 | 3 | 2025-09-19
CCO-121 | Cloud Cost Optimization | Anomaly alerts on daily spend (production) | Alert when daily spend deviates from forecast so surprises are caught within a day instead of at invoice time. | alerting,cost,anomaly,monitoring | Feature | High | Critical | Done | EMP009 | 5 | 2026-07-20 | 2026-07-22
CCO-122 | Cloud Cost Optimization | Rightsize overprovisioned EC2 instances follow-up | Utilization data shows several instances under 15 percent CPU. Rightsize instance types and document the review cadence. | ec2,cost,rightsizing,aws | Task | Medium | Medium | In Progress | EMP005 | 3 | 2026-04-02
CCO-123 | Cloud Cost Optimization | Idle resource detection automation (production) | Detect unattached volumes, idle load balancers, and stopped instances with a scheduled job and report candidates for cleanup. | automation,cost,cleanup,aws | Feature | Critical | Critical | Open | EMP004 | 5 | 2026-05-27
CCO-124 | Cloud Cost Optimization | S3 lifecycle policies for log archives (staging) | Move aging log archives to infrequent access and glacier tiers with lifecycle policies to cut object storage spend. | s3,lifecycle,storage,cost | Task | Medium | Medium | Review | EMP009 | 3 | 2026-06-20
CCO-125 | Cloud Cost Optimization | Reserved instance and savings plan analysis follow-up | Analyze steady-state compute usage and recommend reserved instance or savings plan purchases with projected savings. | cost,analysis,aws,finance | Task | Low | Low | Review | EMP009 | 5 | 2026-07-20
CCO-126 | Cloud Cost Optimization | Cost allocation tagging enforcement follow-up | Enforce required cost allocation tags via policy so spend can be attributed to teams and customers accurately. | tagging,policy,cost,governance | Feature | Critical | Critical | Review | EMP004 | 13 | 2025-10-31
CCO-127 | Cloud Cost Optimization | Grafana cost dashboard per team (production) | Build a dashboard showing spend by team, service, and environment with month over month trend and budget thresholds. | grafana,dashboard,cost,reporting | Feature | Medium | Low | Review | EMP009 | 5 | 2026-07-15
CCO-128 | Cloud Cost Optimization | ElastiCache cluster consolidation (staging) | Multiple underutilized Redis clusters can be consolidated. Plan migration with cache key namespace isolation. | elasticache,redis,consolidation,cost | Task | Critical | Critical | Done | EMP005 | 2 | 2026-07-11 | 2026-07-12
CCO-129 | Cloud Cost Optimization | Kubernetes requests and limits tuning (production) | Overstated resource requests cause poor bin packing and wasted nodes. Tune requests from usage data to reduce cluster cost. | kubernetes,capacity,cost,tuning | Performance | Medium | Medium | Open | EMP004 | 5 | 2026-06-14
CCO-130 | Cloud Cost Optimization | Anomaly alerts on daily spend - phase 2 | Alert when daily spend deviates from forecast so surprises are caught within a day instead of at invoice time. | alerting,cost,anomaly,monitoring | Feature | Medium | High | Done | EMP005 | 13 | 2026-07-19 | 2026-07-25
CCO-131 | Cloud Cost Optimization | Rightsize overprovisioned EC2 instances (staging) | Utilization data shows several instances under 15 percent CPU. Rightsize instance types and document the review cadence. | ec2,cost,rightsizing,aws | Task | High | High | Done | EMP009 | 5 | 2026-05-31 | 2026-06-03
CCO-132 | Cloud Cost Optimization | Idle resource detection automation - phase 2 | Detect unattached volumes, idle load balancers, and stopped instances with a scheduled job and report candidates for cleanup. | automation,cost,cleanup,aws | Feature | High | High | Open | EMP009 | 3 | 2026-07-30
CCO-133 | Cloud Cost Optimization | S3 lifecycle policies for log archives (production) | Move aging log archives to infrequent access and glacier tiers with lifecycle policies to cut object storage spend. | s3,lifecycle,storage,cost | Task | Medium | High | Done | EMP009 | 5 | 2026-07-04 | 2026-07-16
CPDI-105 | Cross-Platform Data Integration | GitHub connector rate limit backoff | Large syncs hit the GitHub REST API rate limit and fail mid-run. Implement exponential backoff and conditional requests with etags. | github,api,rate-limit,bug | Bug | Critical | Critical | In Progress | EMP005 | 2 | 2025-12-08
CPDI-106 | Cross-Platform Data Integration | Jira issue import prototype | Prototype a Jira connector that maps Jira fields into the normalized issue schema, proving the tracker-agnostic model with a second source. | jira,connector,integration,prototype | Feature | Medium | Medium | Done | EMP008 | 13 | 2026-05-10 | 2026-05-23
CPDI-107 | Cross-Platform Data Integration | Webhook-based incremental sync | Replace polling with webhook-driven sync so issue changes appear in the platform within seconds and API usage drops. | webhook,sync,integration,api | Feature | Medium | Low | Done | EMP005 | 5 | 2026-05-20 | 2026-06-03
CPDI-108 | Cross-Platform Data Integration | Normalize status vocabulary across trackers | GitHub, GitLab, and Jira use different status models. Define the canonical status mapping and make it configurable per source. | normalization,schema,integration,design | Task | Medium | Low | Review | EMP008 | 3 | 2026-07-24
CPDI-109 | Cross-Platform Data Integration | GitLab issue import pagination bug | The GitLab importer drops records past page ten because of a pagination cursor bug. Fix and add tests with mocked paged responses. | gitlab,bug,pagination,import | Bug | Low | Low | Open | EMP007 | 8 | 2026-05-11
CPDI-110 | Cross-Platform Data Integration | RabbitMQ queue for sync jobs | Move sync execution onto a message queue with retries and dead letter handling so long imports do not block the API. | rabbitmq,queue,architecture,reliability | Feature | Critical | Critical | In Progress | EMP008 | 5 | 2025-10-14
CPDI-111 | Cross-Platform Data Integration | Field mapping configuration UI | Administrators need to adjust source field mappings without code changes. Build a configuration screen with validation and preview. | configuration,ui,mapping,integration | Feature | Medium | Low | Done | EMP008 | 13 | 2026-07-01 | 2026-07-07
CPDI-112 | Cross-Platform Data Integration | Azure DevOps work item connector | Extend the connector framework to Azure DevOps work items including area path to project mapping. | azure-devops,connector,integration,feature | Feature | Critical | High | Open | EMP005 | 13 | 2026-07-30
CPDI-113 | Cross-Platform Data Integration | Deduplicate issues synced from multiple sources | Issues mirrored across trackers create duplicates. Add cross-source identity resolution using external references. | deduplication,sync,data-quality,design | Task | Medium | Medium | Open | EMP005 | 3 | 2026-06-27
CPDI-114 | Cross-Platform Data Integration | Sync observability: per-run metrics and logs | Emit per-run metrics (records, duration, failures) and structured logs so sync health is visible in Grafana with alerting on failures. | monitoring,metrics,sync,observability | Feature | Medium | Medium | Done | EMP005 | 5 | 2026-03-24 | 2026-04-09
CPDI-115 | Cross-Platform Data Integration | GitHub connector rate limit backoff (production) | Large syncs hit the GitHub REST API rate limit and fail mid-run. Implement exponential backoff and conditional requests with etags. | github,api,rate-limit,bug | Bug | High | High | Done | EMP007 | 2 | 2026-05-01 | 2026-05-22
CPDI-116 | Cross-Platform Data Integration | Jira issue import prototype (production) | Prototype a Jira connector that maps Jira fields into the normalized issue schema, proving the tracker-agnostic model with a second source. | jira,connector,integration,prototype | Feature | Medium | High | In Progress | EMP007 | 5 | 2026-06-08
CPDI-117 | Cross-Platform Data Integration | Webhook-based incremental sync follow-up | Replace polling with webhook-driven sync so issue changes appear in the platform within seconds and API usage drops. | webhook,sync,integration,api | Feature | Critical | High | Review | EMP005 | 3 | 2026-05-26
CPDI-118 | Cross-Platform Data Integration | Normalize status vocabulary across trackers - phase 2 | GitHub, GitLab, and Jira use different status models. Define the canonical status mapping and make it configurable per source. | normalization,schema,integration,design | Task | Medium | Low | Done | EMP005 | 2 | 2026-04-28 | 2026-05-05
CPDI-119 | Cross-Platform Data Integration | GitLab issue import pagination bug - phase 2 | The GitLab importer drops records past page ten because of a pagination cursor bug. Fix and add tests with mocked paged responses. | gitlab,bug,pagination,import | Bug | Low | Low | Done | EMP005 | 8 | 2025-12-28 | 2026-01-13
CPDI-120 | Cross-Platform Data Integration | RabbitMQ queue for sync jobs (staging) | Move sync execution onto a message queue with retries and dead letter handling so long imports do not block the API. | rabbitmq,queue,architecture,reliability | Feature | Low | Medium | Open | EMP007 | 13 | 2026-07-05
CPDI-121 | Cross-Platform Data Integration | Field mapping configuration UI (staging) | Administrators need to adjust source field mappings without code changes. Build a configuration screen with validation and preview. | configuration,ui,mapping,integration | Feature | Medium | Low | Review | EMP008 | 3 | 2026-07-02
CPDI-122 | Cross-Platform Data Integration | Azure DevOps work item connector for EU region | Extend the connector framework to Azure DevOps work items including area path to project mapping. | azure-devops,connector,integration,feature | Feature | Medium | Medium | Done | EMP005 | 8 | 2026-06-11 | 2026-06-29
CPDI-123 | Cross-Platform Data Integration | Deduplicate issues synced from multiple sources - phase 2 | Issues mirrored across trackers create duplicates. Add cross-source identity resolution using external references. | deduplication,sync,data-quality,design | Task | Low | Medium | Done | EMP008 | 8 | 2026-06-04 | 2026-06-14
CPDI-124 | Cross-Platform Data Integration | Sync observability: per-run metrics and logs (production) | Emit per-run metrics (records, duration, failures) and structured logs so sync health is visible in Grafana with alerting on failures. | monitoring,metrics,sync,observability | Feature | High | Critical | Done | EMP005 | 5 | 2026-05-24 | 2026-06-14
CPDI-125 | Cross-Platform Data Integration | GitHub connector rate limit backoff (production) | Large syncs hit the GitHub REST API rate limit and fail mid-run. Implement exponential backoff and conditional requests with etags. | github,api,rate-limit,bug | Bug | Medium | Medium | Done | EMP005 | 2 | 2025-11-16 | 2025-11-26
CPDI-126 | Cross-Platform Data Integration | Jira issue import prototype for EU region | Prototype a Jira connector that maps Jira fields into the normalized issue schema, proving the tracker-agnostic model with a second source. | jira,connector,integration,prototype | Feature | Medium | Medium | Done | EMP008 | 8 | 2026-07-14 | 2026-07-22
CPDI-127 | Cross-Platform Data Integration | Webhook-based incremental sync (staging) | Replace polling with webhook-driven sync so issue changes appear in the platform within seconds and API usage drops. | webhook,sync,integration,api | Feature | Medium | Medium | Review | EMP005 | 3 | 2026-01-21
CPDI-128 | Cross-Platform Data Integration | Normalize status vocabulary across trackers - phase 2 | GitHub, GitLab, and Jira use different status models. Define the canonical status mapping and make it configurable per source. | normalization,schema,integration,design | Task | High | High | Review | EMP007 | 3 | 2025-09-23
CPDI-129 | Cross-Platform Data Integration | GitLab issue import pagination bug for EU region | The GitLab importer drops records past page ten because of a pagination cursor bug. Fix and add tests with mocked paged responses. | gitlab,bug,pagination,import | Bug | Medium | Low | Done | EMP007 | 2 | 2025-12-13 | 2025-12-27
CPDI-130 | Cross-Platform Data Integration | RabbitMQ queue for sync jobs for EU region | Move sync execution onto a message queue with retries and dead letter handling so long imports do not block the API. | rabbitmq,queue,architecture,reliability | Feature | High | Critical | Open | EMP008 | 5 | 2026-05-10
CPDI-131 | Cross-Platform Data Integration | Field mapping configuration UI (staging) | Administrators need to adjust source field mappings without code changes. Build a configuration screen with validation and preview. | configuration,ui,mapping,integration | Feature | Medium | High | In Progress | EMP007 | 8 | 2025-11-07
CPDI-132 | Cross-Platform Data Integration | Azure DevOps work item connector (production) | Extend the connector framework to Azure DevOps work items including area path to project mapping. | azure-devops,connector,integration,feature | Feature | Critical | Critical | Done | EMP008 | 3 | 2025-12-10 | 2025-12-29
CPDI-133 | Cross-Platform Data Integration | Deduplicate issues synced from multiple sources (production) | Issues mirrored across trackers create duplicates. Add cross-source identity resolution using external references. | deduplication,sync,data-quality,design | Task | Low | Low | Done | EMP008 | 3 | 2026-05-17 | 2026-06-06
CPDI-134 | Cross-Platform Data Integration | Sync observability: per-run metrics and logs - phase 2 | Emit per-run metrics (records, duration, failures) and structured logs so sync health is visible in Grafana with alerting on failures. | monitoring,metrics,sync,observability | Feature | Medium | Medium | Done | EMP008 | 8 | 2026-02-02 | 2026-02-07
CPDI-135 | Cross-Platform Data Integration | GitHub connector rate limit backoff (staging) | Large syncs hit the GitHub REST API rate limit and fail mid-run. Implement exponential backoff and conditional requests with etags. | github,api,rate-limit,bug | Bug | Critical | Critical | In Progress | EMP005 | 2 | 2026-07-09
CPDI-136 | Cross-Platform Data Integration | Jira issue import prototype (production) | Prototype a Jira connector that maps Jira fields into the normalized issue schema, proving the tracker-agnostic model with a second source. | jira,connector,integration,prototype | Feature | Medium | Medium | Done | EMP007 | 8 | 2026-03-26 | 2026-04-19
CPDI-137 | Cross-Platform Data Integration | Webhook-based incremental sync (production) | Replace polling with webhook-driven sync so issue changes appear in the platform within seconds and API usage drops. | webhook,sync,integration,api | Feature | Low | Medium | In Progress | EMP005 | 8 | 2026-02-02
CPDI-138 | Cross-Platform Data Integration | Normalize status vocabulary across trackers follow-up | GitHub, GitLab, and Jira use different status models. Define the canonical status mapping and make it configurable per source. | normalization,schema,integration,design | Task | Low | Low | Done | EMP008 | 8 | 2026-02-26 | 2026-03-22
CPDI-139 | Cross-Platform Data Integration | GitLab issue import pagination bug (production) | The GitLab importer drops records past page ten because of a pagination cursor bug. Fix and add tests with mocked paged responses. | gitlab,bug,pagination,import | Bug | Medium | Medium | Review | EMP005 | 3 | 2026-07-22
CPDI-140 | Cross-Platform Data Integration | RabbitMQ queue for sync jobs (production) | Move sync execution onto a message queue with retries and dead letter handling so long imports do not block the API. | rabbitmq,queue,architecture,reliability | Feature | High | Medium | Done | EMP007 | 5 | 2026-05-02 | 2026-05-11